## BSC
Group 1 : Rashmi Dhar, Swati, Sanyogita, Phani, Arvind & Sreenivas
BALANCE SCORE CARD OF A REALESTATE DEVELOPER
Financial Prespective | Measure | Target | Initiative | Internal Business Prespective
Objective | Measure | Target | Initiative | Objective | Measure | Target | Initiative
To increase the profitability of the company | To comapre it with previous fiscal year | Increase in net revenue by 25% | Handing over of projects on time to reduce overheads | To start new projects at prime locations. | To comapre with previous quarter | To launch as least 10 new projects | More joint ventures
|  |  | Start customer referral bonus scheme to employees. |  |  |  | More marketing to increase brand value.
Learning & Growth Prespective |  |  |  | Customer Prespective
Objective | Measure | Target | Initiative | Objective | Measure | Target | Initiative
Improvement in performance of Empolyees | Performance measuring sheets. | To see that more than 80% of employees performance exceeds expectations. | Leadership seminars & workshops on specific lagging issues. | Improvement in customer satisfaction. | Customer feed back forms | Atleast 20% increase in customer happy rating. | Providing empoyees training in quality & CRM.

## Quality Inspection & Test Plan
Group 1 : Rashmi Dhar, Swati, Sanyogita, Phani, Arvind & Sreenivas
PROJECT : CONSTRUCTION OF TOWNSHIP.
Quality Inspection & Test plan
No. | Activity Description |  | Code of |  | Performer/ |  | Approver |  |  | Surveillance by |  |  | Records to be |  |  | Remarks
|  |  | Conformance |  | Checker |  |  |  |  | QC Dept. |  |  | Maintained
5.1 | Excavation in foundations and trenches
5.1.1 | Checking for layout |  | Approved. Drg. |  | Supervisor |  | Site Engineer |  |  | Random |  |  | Joint Record
5.1.2 | Excavation with proper side slopes, Shoring Removing of Water, etc. |  | Approved. Drg. |  | Supervisor |  | Site Engineer |  |  | Random |  |  | ---
5.1.3 | Checking location, firm bed, levels, free from slush |  | As per specifications |  | Supervisor |  | Site Engineer |  |  | Random |  |  | ---
5.1.4 | Disposal/proper stacking of excavated earth in demarked area. |  | As per contract |  | Supervisor |  | Site Engineer |  |  | --- |  |  | ---
5.2 | Back filling in foundation, plinths and trenches
5.2.1 | Determining the maximum dry density and optimum moisture content |  | IS: 2720 |  | QC Engineer |  | Client |  |  | Witness
FCN-LB-06
5.2.2 | Filling and compaction in layers not more than 150mm |  | Specifications |  | Supervisor |  | Site Engineer |  |  | Random |  |  | ---
5.2.3 | Check for degree of compaction |  | IS: 2720 |  | QC Engineer / Site Engineer |  | Client |  |  | Witness |  |  | FCN-LB-05 |  |  | 95% of Maximum dry density.
5.2.4 | Check for final level |  | As per drawing. |  | Supervisor |  | Site Engineer |  |  | Witness |  |  | ---
5.3 | Anti termite treatment
5.3.1 | Material |  | IS:1307, IS:6439 or IS:2682 |  | Manufacturer test certificate |  | QC engineer |  |  | QC engineer |  |  | Checklist, MTCs and MSDS
5.3.2 | Checking for rate of application of dosage as per requirement |  | As per Specifications |  | Specialized Agency |  | Site Engineer |  |  | Random |  |  | ---
5.4 | PCC / lean concrete in plinth/below foundation
5.4.1 | Checking layout, line and level |  |  | Drawing | Supervisor |  | Site Engineer |  |  | Random |  |  | ---
5.4.2 | Establishment of Mix Proportion |  |  | As per Specifications | QC Engineer |  | Client |  |  | Witness |  |  | Mix Design Report
5.4.3 |  | Form work and curing |  | Drawing |  | Supervisor |  | Site Engineer | Random |  |  |  |  | Pour Card
5.5 |  | Concreting for foundations, columns, beams, slab and wall
5.5.1 |  | Adopting mix designs for various grades |  | IS: 456 |  | Supervisor |  | Site Engineer |  |  | Witness |  |  |  | Design Mix / Concrete Pour Card
5.6 |  | Form work
5.6.1 |  | Preparatory works for steel / plywood |  | As per specifications/drawings |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | ---
5.6.2 |  | Fixing and positioning in location for shuttering works and supports etc. |  | Drawing |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | Pour Card
5.6.3 |  | Checking of alignment, vertical dimension, coordination etc in line with construction drawing. |  | Drawing |  | Supervisor/ |  | Site Engineer |  |  |  | Random |  |  | FCN-BB-03
Surveyor
5.7 |  | Rebar work
5.7.1 |  | Preparation submission and approved of BBS in line with construction drawing |  | Drawing |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | BBS
5.7.2 |  | Lot approval |  | IS:1786 |  | QC engineer |  | Client |  |  |  | IS: 1786 |  |  | 3rd party test report and MTCs
5.7.3 |  | Straightening , cutting, bending and binding in position of rebar work as per drawing |  | IS:456, Drawing |  | Site Engineer |  | Client |  |  |  | Random |  |  | FCN-BB-03
5.7.4 |  | Checking and fixing metal inserts/bolts as per drawing in location. |  | Drawing |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | FCN-BB-03
5.8 |  | Concreting
5.8.1 |  | Preparation and check of temporary arrangement of staging, pump, chute, walkway, machineries etc... |  | Specification |  | Supervisor |  | Site Engineer |  |  |  | --- |  |  | ---
5.8.2 |  | Mixing, pouring and placement of fresh concrete including admixture |  | Mix Design |  | Supervisor |  | Site Engineer |  |  |  | Witness |  |  | FCN-BB-03, check list
5.8.3 |  | Check of slump/ |  | Mix Design |  | Supervisor/ |  | QC Engineer |  |  |  | Witness |  |  | FCN-BB-03
|  | w/c ratio |  |  |  | Lab Tech.
5.8.4 |  | Sampling and testing of Cubes |  | Mix Design, IS:456, IS 516, IS:1199 |  | Supervisor/ |  | QC Engineer |  |  |  | Witness |  |  | FCN-BB-03
Lab Tech.
5.8.5 |  | De shuttering with adequate precautions. |  | IS 456 / as per specification |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | ---
5.8.6 |  | Curing of Concrete |  | IS 456/as per specification |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | ---
5.8.7 |  | Check of visual inspection of concrete surface and rectification of unsatisfactory performance, if any |  | Specifications |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | FCN-BB-03 / FCN-CC-01
5.9 |  | Brick / Block Masonry /Random rubble work
5.9.1 |  | Procurement of Bricks of approved brand which satisfies specifications |  | Specification |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | FCN-LB-09
5.9.2 |  | Shifting and handling with proper care |  | Specification |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | ---
5.9.3 |  | Mixing and preparation of cement mortar |  | Drawing/Spec |  | Supervisor |  | Site Engineer |  |  |  | Random /Witness |  |  | ---
5.9.4 |  | staging and scaffolding |  | --- |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | ---
5.9.5 |  | Checking of bond, joints, thickness, true line, levels, verticality |  | Drawing |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | FCN-CC-01
5.9.6 |  | Check for curing |  | Specification |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | ---
5.1 |  | Plastering
5.10.1 |  | Preparatory arrangement of surface preparation like raking of joints removal of loose mortar and fixing chicken mesh at RCC and BW joints and wetting the surface |  | Specification |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | ---
5.10.2 |  | Sand |  | IS:1542 |  | QC |  | Client |  |  |  | For every lot received at site |  |  | Test report
5.10.3 |  | Cement |  | IS:269, IS:1489 P-1, IS:8112 |  | QC |  | Client |  |  |  | For every lot |  |  | MTCs, test reports
5.10.4 |  | Proportion of cement mortar, mixing and placing in location |  | Drawing/Spec |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | ---
5.10.5 |  | Checking of alignment thickness, verticality in line of construction drawing |  | Drawing / Specification |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | FCN-CC-01
5.10.6 |  | Curing |  | Specification |  | Supervisor |  | Site Engineer |  |  |  | Random |  |  | ---

## Quality Testing Metrics
Group 1 : Rashmi Dhar, Swati, Sanyogita, Phani, Arvind & Sreenivas
PROJECT : CONSTRUCTION OF TOWNSHIP
QUALITY TESTING METRICS
Sr. No. | Title | Doc. No. | Frequency of Test / Check | Relevant IS Codes
6.1 | Soil |  |  | IS:2720
6.1.1 | Core cutter test | FCN-LB-05 | At every 100 m2 of compacted area for small plinth filling At every 500 m3. of compacted earth filling for mass filling work
6.1.2 | Standard Proctor Test | FCN-LB-06 | Once for each source of earth using for backfilling
6.2 | Coarse Aggregate / Fine Aggregate |  |  | IS:2430 – 1986
6.2.1 | Specific gravity(CA&FA) | FCN-LB-04 | Once for site or Change in source
6.2.2 | Bulkage of Sand (FA) | - | In monsoon/Rainy season when concreting is done by volumetric batching this test is to be performed daily and necessary Bulkage corrective to be applied
6.2.3 | Dry/Loose Bulk density(CA&FA) | - | As and when required
6.2.4 | Silt content in Sand (FA) | FCN-LB-07 | For each source
6.2.5 | Aggregate impact value(CA) | FCN-LB-08 | If the source explored between 501-1500 cum take one gross sample at each 100 cum.
6.2.6 | Sieve analysis of aggregate(CA&FA) |  | If the source explored between 1501-5000 cum, take one gross sample at each 200 cum.
6.2.7 | Aggregate crushing value(Coarse Aggregate)
6.2.8 | Flakiness Index or Thickness Test(Coarse Aggregate) | FCN-LB-08
6.3 | Bricks/ Solid concrete blocks |  |  | IS:5454-1978
6.3.1 | Visual Check | - | Total 20 Nos. of Bricks to be selected from the trucks (i.e.; 6 to 7 bricks from each Truck)
6.3.2 | Dimensional Check | -
6.3.3 | Water absorption | FCN-LB-09 | For each source Random 3 Nos. to be tested from 20 Nos. of bricks as selected in 6 (i) & 6(ii)
6.3.4 | Compressive strength
6.4 | Cement | IS:3535, IS:4031 | For each batch received at site. | IS:269, IS:8112 and IS:12269
6.4.1 | Fineness of cement | Manufacturer
6.4.2 | Standard consistency of cement | Test certificate or
6.4.3 | Setting time initial/Final | Outside laboratory or
6.4.4 | Compressive strength | FCN-LB-12
6.4.5 | Soundness
6.5 | Reinforcement Steel |  |  | IS: 1786-2008
6.5.1 | Rolling margin | FCN-LB-15 | For bar dia. Upto 10mm – One sample from each 25 ton or part thereof
For bar dia. Above 10mm and upto 16mm – One sample from each 35 ton or part thereof
For bar dia above 16mm – One sample from each 45 tone or part thereof
One sample consists of 3 Nos. of bars of at least 0.5m length
6.5.2 | Tensile Test | Manufacturer Test Certificate or Test Report from outside laboratory. | For each lot received at site.
6.5.3 | Elongation
6.5.4 | Bend – Rebend test
6.6 | Concrete |  |  | IS: 456-2000
6.6.1 | Slump Test | FCN-LB-10 | For each concrete cube set | IS:1199 &
6.6.2 | Compressive strength |  | The cube samples shall be taken for each grade of concrete for following daily concrete quantity
Qty. of concrete in Cum.(Daily) No. of Samples
1 – 5 1
6 – 15 2
16 - 30 3
31 - 50 4
51 and above 4 plus one set for each 50 Cum of concrete
|  |  | One sample consists of 3 nos of cubes, for 28 days strength. However where 7 days strength is required the sample size may be increased to six nos of cubes for 7 days strength also. | IS: 516
Standard deviation to be taken.
The frequency mentioned above is to maintain for initial period, till consistent results are obtained. It may be reduced as per engineer in-charge’s discretion
6.13 | Tiles | Check list | Water absorption test (mosaic, glazed floor)
|  | Test reports | Water transverse test (mosaic)
|  | MTCs | Abrasion resistance (mosaic) or impact test (glazed)
Dimensions and size control
Glue performance: tearing out test
Acid and Alkali resistance (glazed)
6.14 | Calibration of test equipment | FCN-LB-01 | Compression testing machine-yearly once or change of site by 3rd party.
Other measuring equipments-yearly once
6.15 | Inspection and test status | FCN-CC-01 | Daily inspection of site activities | Refer QMP-CN-03
6.16 | Control of nonconforming product | FCN-CC-03 | On occurrence of Nonconformity | Refer QMP-NP-01
6.17 | Notification to customer | FCN-CC-02 | On receipt of non-conforming material supplied by customer / client | Refer QMP-CN-08
6.18 | Weekly review report | FCN-LB-16 | To be Submitted to RO QA/QC – Weekly

## Communication Management Plan
Group 1 : Rashmi Dhar, Swati, Sanyogita, Phani, Arvind & Sreenivas
COMMUNICATION MANAGEMENT PLAN FOR CONSTRUCTION INDUSTRY.
Communication Type | Objective of Communication | Medium | Frequency | Audience | Owner | Input / Deliverable | Format
Kickoff Meeting | Introduce the project team and the project. Review project objectives and management approach. | · Face to Face | Once | · Project Sponsor | Project Manager | · Agenda | · Soft copy archived on project SharePoint site and project web site
|  |  |  | · Project Team |  | · Meeting Minutes
· Stakeholders
Project Team Meetings | Review status of the project with the team. | · Face to Face | Weekly | · Project Team | Project Manager | · Agenda | · Soft copy archived on project SharePoint site and project web site
|  | · Conference Call |  |  |  | · Meeting Minutes
· Project schedule
Technical / Design Review Meetings | Discuss and develop technical design solutions for the project. | · Face to Face | As Needed | · Project Technical Staff | Technical Lead | · Agenda | · Soft copy archived on project SharePoint site and project web site
· Meeting Minutes
Monthly Project Status Meetings | Report on the status of the project to management. | · Face to Face | Monthly | · PMO | Project Manager | · Slide updates | · Soft copy archived on project SharePoint site and project web site
|  | · Conference Call |  |  |  | · Project schedule
Project Status Reports | Report the status of the project including activities, progress, costs and issues. | · Email | Monthly | · Project Sponsor | Project Manager | · Project Status Report | · Soft copy archived on project SharePoint site and project web site
|  |  |  | · Project Team |  | · Project schedule
· Stakeholders
· PMO