## GROUP-3
PROJECT NAME | Blue Bank Virtual Cheque Deposit
PROJECT OBJECTIVE | 1. To launch special scanner app to get the necessary images to make the electronic deposit.
2. To increase customer using digital platform, retention rate and Customer base
3. To establish 24/7 service support team
SPJIMR - BATCH 33 - GROUP 3
APPLICATION ID | PARTICIPANT NAME
SPJ1116 | YUKTI GUPTA
SPJ1115 | ROHIT SADAPHAL
SPJ1117 | MILIND SONAWANE
SPJ1119 | ANIRUDH BHARDHWAJ
SPJ1120 | ASHOK
SPJ1118 | RAVINDRA SINGH

## 1 Balance Score Card
| Objective | Measures | Target | Initiatives
Financial | Reduce Operational Cost | Monthly operational cost tracked | Reduce by 10% | Quality Management of Virtual Cheque Management Project
| Reduce Overhead Cost | Monthly overhead cost tracked | Reduce by 20% | Invest in Employee productivity measures
Customer | Increase Customer Experience | Customer feedback of 24*7 support service | Increase is Customer Experience score by 20% | - Setup pan India 4 dedicated customer care centers - Provide regional language support executives to support regional lingual customers
| Increase Customer Satisfaction | Customer Quarterly Feedback | Customer Satisfaction score increased by 30% | Monthly check-in with customers on issue resolution and support
| Increase Customer Loyalty | Increase in Customer investments in the bank | Deposits increased by 20% | Introduce Customer Loyalty program
Internal | Improving Existing Digital Products | Increase in customers enrolling for the digital products as well as new customers opening account in bank | 10% hike in New Accounts Opened 50% of existing customers adopting the digital products and its features >200K downloads of Scanner App launched by the bank | Initiate existing digital product assessments to identify improvement areas. Implement improvement areas. Launch marketing campaigns to create awareness and buzz around the improved digital products
| Automating Processes | Decrease in operational costs | Reduce operational cost by 5% | Find a reliable technology partner Invest in new age banking technology
| Reducing Number of Branches | Reduction in number of customers visiting the Bank | Reduced by 15% | Successful launch and adoption of Virtual Cheque System
Innovation & Learning | Develop Banking Mobile App | Time to market with first product | Launch by Sep-20 | Incentivizing the early adopters
| Employee Growth | Promote digital learning | Train employees in batches in 100 days | Tie up with SME and trusted education partners
| Virtual Assistant | Customer Engagement | Launch by Sep-20 | Create a chatbot application for prompt and personalized experience to customers

## 2 Quality Testing Plan
Quality Test Plan - Virtual Cheque Deposit System
Task ID | Task Name | Owner
1 | Test Planning
1.1 | Review and analyze the requirements | Test Manager
1.2 | Define Scope of Testing | Test Manager
1.3 | Get Approval on Testing Scope | Test Manager
1.4 | Design Test Strategy | Test Manager
1.5 | Get Approval on Test Strategy | Test Manager
1.6 | Identify required tools needed for testing and management | Test Manager
1.7 | Estimate Test Effort and Team | Test Manager
1.8 | Get Approval on Test Effort and Team | Test Manager
1.9 | Define Test Schedule | Test Manager
1.10 | Determine and procure the test environment | Test Manager
2 | Test Design
2.1 | Create Test Plan | Test Manager
2.2 | Test Plan Review and Approval | Test Manager
2.3 | Develop Test Cases | Test Lead
2.4 | Test Cases Review and Approval | Test Manager
3 | Test Environment Set-Up
3.1 | Procurement of Machineries | Project Manager
3.2 | Installation of Machineries | IT Manager
3.3 | Physical infrastructure Completion | IT Manager
4 | Test Execution
4.1 | Release 0.1
4.2 | Acceptance Test | Test Lead
4.3 | Functional Test | Tester
4.4 | Report Defects | Tester
4.5 | Regression Test | Tester
4.6 | Publish Test Reports | Test Lead
4.7 | Release Sign Off | Test Manager
4.8 | Release 0.2
4.9 | Acceptance Test | Test Lead
4.10 | Functional Test | Tester
4.11 | Report Defects | Tester
4.12 | Regression Test | Tester
4.13 | Publish Test Reports | Test Lead
4.14 | Release Sign Off | Test Manager
5 | Integration Test
5.1 | Acceptance Test | Test Lead
5.2 | Functional Test | Tester
5.3 | Report Defects | Tester
5.4 | Regression Test | Tester
5.5 | Publish Test Reports | Test Lead
5.6 | Integration Sign Off | Test Manager
6 | User Acceptance Test
6.1 | Third party user review | User Tester
6.2 | Report Defects | User Tester
6.3 | Regression Test | User Tester
6.4 | User Acceptance Test Sign Off | Test Manager
6.5 | Launch of Product | Project Manager

## 3 Testing Quality Metrics
Virtual Cheque Deposit System
S No. | Testing Metric | Data received during test case development & execution | %
1 | No of Requirements | 20
2 | Average No of Test Cases Per Requirement | 20
3 | Total Test Cases for all requirements | 400
TEST COMPLETION STATUS
1 | Total No of Test Cases Executed | 350 | 87.5%
2 | Total No of Test Cases not executed | 50 | 12.5%
TEST EXECUTION STATUS
1 | No of Test Cases Passed | 210 | 60%
2 | No of Test Cases Failed | 90 | 25.71%
3 | No of Test Cases Blocked | 50 | 14.29%
4 | Total No of Defects Identified | 120
DEFECT STATUS BY PRIORITY
1 | Critical Defects Count | 20 | 16.67%
2 | High Defects Count | 20 | 16.67%
3 | Medium Defects Count | 50 | 41.67%
4 | Low Defects Count | 30 | 25%
FINAL DEFECTS STATUS BEFORE LAUNCH
1 | Defects Accepted as Valid by Dev Team | 100 | 83.33%
2 | Defects deferred for future releases | 20 | 16.67%

## 4. Project Communication
Communication Type | Objective | Delivery Method (Communication Channel) | Sender | Audience | Frequency | Format
What type of communication needs to be delivered? | What is the objective of the communication? | How will the communication be delivered? | Who will the communication be from? | Who all will receive the communication? | When will it happen and how often? | Format Used
Kick Off Meeting | Introduction of project team and stakeholders, review of project objective and expectations | Face to Face | Project Manager | Project sponsor, Project team, Stakeholders | Once, Start of the Project | NA
Weekly Status Report | Sharing project status across schedule, cost, risks, quality. | Email, SharePoint | Project Manager | All Project Team Members & Relevant Stakeholders | Weekly | Weekly Status Report Template.docx
Collaboration Messages | Discussion on work status, Cross team collaboration, Achievements and Breakthroughs | Microsoft Teams | All Project Team Members | All Project Team Members | Daily | NA
Quality Governance Report | Share Performance Indicators, Quality Status, Testing Status and Results | Email | Quality Manager | All Project Team Members & Relevant Stakeholders | Fortnightly | Quality Governance Report Template.docx
Team Meetings | Discuss each team member status, support needed, risks/issues and targets for the week | MoM, Email, Microsoft OneNote | Project Manager | All Project Team Members | Weekly | NA
Escalations | Raise any project issues or concerns | Email | Project Stakeholders | Project Manager | As and when required | NA
Release Notifications | Sharing release of the project milestone | Email | Project Manager | All Project Team Members & Relevant Stakeholders | When a release is scheduled | Release Notification Template.docx
Project Review Meeting | Review Project status, schedule, cost etc. | Face to Face, VC | Project Manager | All Project Team Leads & Relevant Stakeholders | Fortnightly | NA
Stakeholder Updates | Summary of Achievements, Challenges, Risks/Issues, support needed from leadership and way forward | Email, Meeting | Project Manager | Stakeholder and Senior Leadership | Monthly | NA
Project Closure Meeting | Summary of lessons learned, assessment of critical work packages and scheduling of future tasks and maintenance activities | Meeting | Project Manager | All Project Team Members & Relevant Stakeholders | Once, End of the Project | NA