## Communication Plan (Jal Mahal)
| Description | Frequency | Method | Audience | Owner
S.No. | Name of the Communication | How Often it Happens | Method of Communication | Who will receive the communication | Who is responsible
1 | Progress Meeting (Schedule) | Weekly | In Person/Microsoft Team | Project Head | On Field Incharge
2 | Project cost status | Fortnightly | In Person/Microsoft Team | Finance Team, Project Head and CEO | Project Manager
3 | Procurement Status | Weekly | In Person/Microsoft Team | Project Head, Project Manager, Finance Team | Procurement Lead
4 | Design Status Meeting | Weekly | In Person/Microsoft Team | CEO, Project Leadership Team | Technical Lead
5 | Lab Report Update | Fortnightly | In Person/Microsoft Team | Project Head, Project Manager, Leadership Team | Civil Construction Lead
6 | HR Update | Fortnightly | In Person/Microsoft Team | Project Head, Project Manager | HR Lead
7 | Risk Assessment/Strategy | Weekly | In Person/Microsoft Team | Project Head, Project Manager, Leadership Team | Risk Manager