## Jal mahal Project
Preventive Quality metrics
| Division | Active deliverbales in project | Quality plan | Quality Evaluation | Pre-Installation meetings | Best practices
Sno |  |  | Number of milestone in deliverables with out quality plan within 60 days of mobilization | Number of milestones in deliverables with out quality evaluation within 45 days of mobilization | Number of milestones in deliverables executing work without a pre-installation meeting | Number of milestones in deliverables Not accessing Best practise with in 30 days
1 | Civil construction | Construction of a channel to divert the city drain | 1 | 5 | 3 | 2
2 | Aquatic life division | Increasing aquatic life to lake via scientific injection of new fish species | 2 | 4 | 0 | 3
3 | Architect division | Bubblers/fountain in the lake | 0 | 3 | 3 | 2
4 | Water division | Water quality to sustain marine life as per WHO standards | 1 | 7 | 2 | 4
5 | Bird life division | Developing nesting islands | 2 | 5 | 4 | 5
| Project |  | 6 | 24 | 12 | 16
Quality Incident metrics
| Division | Active deliverbales in project | Water infiltration | Missed key project activity | Major rework | Failed Test
Sno
1 | Civil construction | Construction of a channel to divert the city drain | Due to monsoon the construction was delayed and resulted in 12 days delay cost, resulting additional cost of INR 2,50,00 | none | Rework on drainage pipe of lenth 5 meters costing extra INR 5,00,000 | none
2 | Aquatic life division | Increasing aquatic life to lake via scientific injection of new fish species | None | none | Few fish eggs failed to incubate in three attempts several attempt wre made to breead some specific fish species, re qork costed INR 3,00,000 | Lab test of lake water suitable for fishes breeding failed
3 | Architect division | Bubblers/fountain in the lake | Monsoon delayed , delay costed INR 1,00,000 | Foundation depth missed by 2 meters | Rework on re-painting the design on the fountains costing INR 2,00,000 | None
4 | Water division | Water quality to sustain marine life as per WHO standards | None | none | none | Faile the test as water quality was not suitable for marine life . Till water treatment was done to bring it to a level where it can nourish life
5 | Bird life division | Developing nesting islands | Delayed by monsoon | Electric fencing missed | Fencing reqork | None
Note on D14: Reena: a water event (weather, site, system) that resulted in effort to clean up or damage to existing construction
Note on F14: Reena: any activity the project team committed to in their quality plan that they subsequently did not accomplish
Note on H14: Reena: any rework above a set cost (for example, $2,500) to any party - owner, designer, contractor or trade contractors; or any rework that impacts the project's critical path by one day or more
Note on J14: Reena: any test that fails for which the project team had expected to pass