## Quality Control
| Applicable to Each Wave | Standard Set of Documents and Practices to be applied for All Waves
1 | Business Excellence Team onboarded | a) | Detail process documentation | SIPOC, HLPM, DLPM
1 | Send request for the BE Coach and Assessor | b) | Process Metrics | Cause & Effect, Data collection plan, Transfer Function
2 | BE Coach and Assesor identified | c) | 3 by 3 Matrix
3 | Create and Agree on BE Deployment Plan | d) | FMEA - Project Transition
4 | BE Deployement | e) | FMEA - Process
2 | Project Planning | f) | Process Controls
3 | Service Management Framework | g) | Visual Management
a) | Define and Establish the Service Management Framework | h) | Management Operating System
b) | Service Management Framework Signed Off
c) | Roll out of the Service Management Framework
4 | KPI and SLA
a) | Define KPI and SLA
b) | Confirmation Service Management and Operational Metric Data Collection Plan
c) | Confirm Service Baseline
d | Review and Agree on KPI/SLA with Client
e) | SLA and KPI Agreed and Signed Off
5 | Business Continuity Plan
a) | Business Recovery plan defined and Critical processes identified
b) | Confirm SLA and KPI reporting level (regionally/globally etc)
6 | Knowledge Transfer Planning (Gate 2 & 3)
a) | Scorecard and Audit Approach created
b) | Project team to review and discuss approach
c) | Review Audit criteria provided by Operations team
d | Update the Gate 2 and Gate 3 scorecard basis the input from the SME
e) | Roll out the Dashboard and QA approach to Client SME and Operations SME
7 | Roll out the Dashboard and QA approach to Client SME and Operations SME
a) | Create Remediation Plan
b) | Project team to review and discuss approach
c) | Remediation plan agreed and finalised
d | Roll out Remediation plan to Client SME and Operations SME
8 | Conduct Gate 1 assessment
a) | Finalise performance report and recommendations
9 | Conduct Gate 2 assessments
a) | Finalise performance report and recommendations
10 | Conduct Gate 3 assessments
a) | Finalise performance report and recommendations
11 | SRT Quality Framework
a) | Create QA approach and Framework (Sampling, Targets, Ramp Down)
b) | Review QA approach with Client
c) | SRT QA approach and framework finalised and agreed
12 | Operations Support Plan
a) | Identify the support team
b) | Agree on the responsibility matrix
c) | Review and Agree on the reporting approach
d | Proposed metric and measure plan agreed
13 | SRT Metrics and Reporting
a) | Review the SRT Metrics and Measurement Plan and Review with client
b) | SRT metrics finalised and agreed
c) | Create SRT reporting format and MOS
d | Review SRT format and MOS with the client
e) | SRT reporting and MOS finalised and agreed
14 | SRT assessment conducted and reporting shared as planned
15 | Conduct the following BE assessment post GO Live (standard checklist org. wide)
a) | Pre Go Live (5 days before)
b) | Day 1 assessment
c) | Day 7 Assessment
d | Day 30 Assesment
e) | Day 60 Assessment
f)' | Day 90 Assessment
16 | Handover document for Quality from Project Management to Operations team

## Process Overview
Process Overview

## Communication Plan
General Structure for Communication Plan - as being used in current project (may be tweaked basis requirement of the key stakeholders)
Participants
Event | Agenda | Frequency | Owner | Project Team | Client | Propose Day(s) | Duration | Time
TBD
Weekly Joint Transition Meeting | - Workstream by Workstream Brief Status - Joint view including dependencies (including items on Critical Path, actions and mitigations) | Weekly | Transition Lead | Account Lead | Client Transition Lead | TBD | 1 Hour | TBD
| - Discussions on RAID log & Actions/Decisions |  | Client Transition Lead | Workstream Leads | Client Workstream Leads
Wave KT Joint Team Checkpoints | - Walkthrough status update including critical path activities and current state | Weekly | Wave KT Lead | Wave KT Lead and any other Team members | Client Wave Lead and other team members | TBD | 1 Hour | TBD
- Discuss risks and mitigating actions
- Discuss issues to be escalated for the joint weekly transition meeting
Technology Joint Team Checkpoints | - Walkthrough status update including critical path activities and current state | Weekly | Tech Lead | Tech Lead | Client Tech Lead | TBD | 1 Hour | TBD
- Discuss risks and mitigating actions
| - Discuss issues to be escalated for the joint weekly transition meeting |  |  |  | Client team members as necessary
|  |  |  | Transition Lead | Client Transition Lead
PMO Lead
Joint Review Board Governance Meeting | - Set and Monitor status and Strategic direction | Quarterly | Account Lead | Account Lead | Client Executive Sponsors | TBD | 1 Hour | TBD
| - Establish business vision |  |  | Delivery Executive | Client Transition Lead
| - Resolve strategic or escalated issues |  |  |  | Client Team POC
|  |  |  | Transition Lead | Client Program Lead
PMO Lead
Transition Governance Committee Meeting | - To review overall Program Progress | Monthly | Transition Lead | Account Lead | Client Transition Lead | TBD | 1 Hour | TBD
| - To report overall Program Progress to Executive sponsors |  | Client Transition Lead | Global Transition Lead | Client Program Lead
| - To escalate Program issues/risks to Executive sponsors |  |  | PMO Lead | Client SME
Client Transition Lead and Transition Lead Weekly Catch up | - To discuss project planning, key issues and upcoming events | Weekly | Transition Lead | Transition Lead | Client Transition Lead | TBD | 30 Mins | TBD
Client SME