## Team Details
Group 7
Assignment Given By : | Prof. Chaitanya Sabne
Group Members : | Gaurav Aggarwal
Gopala Krishnan P
Atinder Sodhi
Stephen Salve
Assignment Includes : | 1 - Balance scorecard
2 - Project planning
3 - Quality Testing Plan
4 - Commication Mamangement Plan

## 1.Balance scorecard
Demirt - definitation
Demerit is the score given by external auditor during the audit finished vehicle. The demirt score is an internatinal Quality measuring parameter, which is comparitve intecater to compare the vehciles with other brand or same branded vehicle produced in other plant.
Customer |  |  |  | Financial
Objectives | Measures | Target | Initiatives | Objectives | Measures | Target | Initiatives
Improve Demert point at audit level should be less than 20 | Success : Demerit score < 20 Failure : if Demerit score > 20 | Demerit score should be < 20 to announce SOP | 1. Level- 2 auditor to audit the vehicle 2. Creat awaressnes for part handling 3. Training for part assembly as per standards | incease in cost of poor quality | Success : Conversion cost is with in budget Failure : Conversion cost is crossing the buget | Cost control and monitor with in budget to control with in 20 Demerit point | 1. Part quality report to be monitored and cost impact to be monitored 2. Supplier cost control 3. Audit the rejection area
Learning & Growth - Internal |  |  |  | Process - Internal
Objectives | Measures | Target | Initiatives | Objectives | Measures | Target | Initiatives
To have everyone on the consulting team confident in their ability to identity the defect in the part and at vehicle level to achieve targeted score | Success : Demerit score < 20 Failure : if Demerit score > 20 | part defet to be monitored by each agreegate heads | 1. PPAP of parts which contribute major demerit points to be reaudited 2. Special task team formed to take quality initiatives to train the audit team starting from part till vehcile level | Consitent development in the new processes and products both at part level and vehcile level | Success : Monthly reduction in the demerit score thought part quality development Failure : Monthly reduction trend not monitored and improvement not done on desired parts | at least 5 major task completed in each area - part, process, design, | 1. Process divided in to zones for focused monitoring 2. parts divided in to catagoreis as per demerit scores 3. Action plan alinged to achiech demerit score 4. Training given to all involved team members from all the three areas Part, Process, desing

## 2 - Project planning
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
|  |  | 2020-04-01 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
|  |  | 2020-06-30 |  |  | 85
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
1 | PROJECT CONCEPTION AND INITIATION | Complete |  |  |  | 39
1.1 | – Project Charter | Complete |  |  |  | 10
1.1.1 | –– Project Charter Revisions | Complete |  |  |  | 5
1.2 | – Research | Complete |  |  |  | 45
1.3 | – Projections | Complete |  |  |  | 11
1.4 | – Stakeholders | Complete |  |  |  | 14
1.5 | – Guidelines | In Progress |  |  |  | 14
1.6 | – Project Initiation | In Progress |  |  |  | 19
2 | PROJECT DEFINITION AND PLANNING | In Progress |  |  |  | 18
2.1 | – Scope & Goal Setting | On Hold |  |  |  | 10
2.2 | – Budget | In Progress |  |  |  | 3
2.3 | – Communication Plan | In Progress |  |  |  | 9
2.4 | – Risk Management | Complete |  |  |  | 9
3 | PROJECT LAUNCH & EXECUTION | Complete |  |  |  | 38
3.1 | – Status & Tracking | In Progress |  |  |  | 3
3.2 | – KPIs | In Progress |  |  |  | 6
3.2.1 | –– Monitoring | In Progress |  |  |  | 9
3.2.2 | –– Forecasts | Not Started |  |  |  | 3
3.3 | – Project Updates | Not Started |  |  |  | 2
3.3.1 | –– Chart Updates | In Progress |  |  |  | 31
4 | PROJECT PERFORMANCE / MONITORING | In Progress |  |  |  | 31
4.1 | – Project Objectives | In Progress |  |  |  | 4
4.2 | – Quality Deliverables | On Hold |  |  |  | 7
4.3 | – Effort & Cost Tracking | Not Started |  |  |  | 11
4.4 | – Project Performance | Not Started |  |  |  | 24
5 | PROJECT CLOSER | Not Started |  |  |  | 3
5.1 | – Handing Over Document | Not Started |  |  |  | 11
5.2 | – Go Live for Production | Not Started |  |  |  | 24

## 3-Quality Testing Plan
QUALITY TESTING PLAN - TESTING METRICS
S.No | Testing Metric | Data retrieved during test case development & execution
1 | Functional Requirements Gathering | 8 | Test Completion Status
2 | Avg.test cases created per requirement | 10
3 | Total no.of test cases created | 80
4 | Test Cases Planned | 80
4.1 | Total No Test cases executed | 70
| No of Test Cases Passed | 45
| No of Test Cases Failed | 15
| No of Test Cases Blocked | 10
4.2 | Test Cases not executed | 10
4.3 | Number of Defects identified | 20
| Critical Defects count | 4
| High Defects Count | 5
| Medium Defects Count | 6
| Low Defects Count | 5
4.4 | Number of Defects Status | 20
| Defects Closed | 16
| Defects Open | 4
ROOT CAUSE ANALYSIS FOR TEST CASES FAILED
1). | Inadequte Trained Resources
2). | Lack of business understanding
3). | Lack of technical knowledge
4). | Shortfall in communication by client
5). | Lack of Planning
6). | Lack of understanding in Dominee knowledge
7). | Missing Requirement

## 4 - Commication Mamangement Pla
Project Manager | Stephen
Project Sponsor | Gaurav A, Gopala Krishnan
Project Lead | Atinder
Technical Consultant | Chaitanya Sabne
Commiunication | Method | Frequency | Goal | Owner | Audience | MOM Owner
UX Review Meeting | Meeting.(Share design Before the Meeting) | Phases | Review all the Design.Take feedback.Make changes and get approval on the Design | Project Manager | Project Lead + Customer + Project Sponsor + Designer | Project Manager
Feature Groooms /Product Grooming | Meeting(List of Feature/Deign/flow. Pre Read) | Phases | Grommong the project team on all the feature to be build during this Phase | Project Manager | Project Team+ Technical Staff + Directy working in those phases +Customer | Project Manager
Project Status Report | Email | Weekly | Review project Status | Project Manager | Project Team + Project Sponsor + Customer | Project Manager
Team Standup | Meeting | Daily | Discuss what each team member did yesterday, What they'll do today and any blockers | Project Lead | Project Team | Scrum Master
Project Review | Meeting | monthly | Present Project Deliverables, gather feedback and discuss the next steps | Project Manager | Project Team + Project Sponsor + Project Lead* + Customer | Project Manager
Post Mortem Meeting | Meeting | At end of Project. | Assess what worked and what did not work and discuss actionable takeways | Project Sponsor | Project Team + Technical Consultant | Scrum Master
Task Progress Update | Team Gantt | Daily | Share Daily Progress made on Project Tasks | Project Manager | Project Team | Scrum Master
Project risk | Meeting | Bi-weekly | Reviewing all the Risk from the Risk Register. | Project Manager | Project Team + Risk Manager | Scrum Master
* is Mandatory