## Exercise 1 Balance scorecard
Group 5: | Ranjit Phaltane, Souren Laha, Siddhant, Thiyagarajan, Roshan, Ramcharit
Project objective: Develop a automotive project for domestic market by XXXXXXX
BALANCE SCORE CARD
| Objective | Measure | Target | Initiative | Objective | Measure | Target | Initiative
| CUSTOMER |  |  |  | FINANCE
| Achieve XXX JD Power - best in segment in 20XX study | Customer ratings by external agency | Best in segment (eg. Score 900 / 1000) | Alpha & beta testing Customer field trials 50k km road endurance across India | Achieve product gross margin | Contribution % per veh (based on variable costs) | Achieve 1% higher than existing product in same segment | Variable cost assessement in direct & indirect areas & control Pricing proposals
| Achieve Customer satisfaction in first 3 months warranty | Def / 100 veh from 1st & 2nd service data of vehicles | Below 50 def / 100 veh | Product durability testing APQP & PPAP processes for inhouse & supplier parts Reliaility score | Lowest warratny cost | ₹ / veh | Warranty cost below ₹ 100 / veh for 24 M warranty | Warranty only thr online DMS Confirmation by TM service for warranty item
| LEARNING & GROWTH (INTERNAL) |  |  |  | PROCESSES (INTERNAL)
| Implement zero rejection for in house machined parts (cylinder block) | Honing process capability | Achieve Cpk of 2 from existing 1.1 | New Honing MFG method Servo hyd honing m/c commissioning & programming, setting etc | Zero rejection for in house machined parts | Process capability | Cpk > 2 | Refurbishment of old m/c In process inspection Better coolant management for m/c Single stage - fine m/c operations
| Engine heat complaint resolution | Customer feedback on engine heat after city ride | No complaint after 50 km ride after city ride in traffic during 40 deg C atm condition (in pilot testing) | Thermal management initiatives using CFD Consultancy from XXXX | Low rework @ Engine & vehicle assembly | % rework per shift | < 5% / shift | Process validation trials during beta assembly m/c & fixtures - process proving & capability

## Exercise 2-Q plan
Group 5: | Ranjit Phaltane, Souren Laha, Siddhant, Thiyagarajan, Roshan, Ramcharit | [12 empty] | Note - List of activities required is provided. Schedule is not created
Project objective: Develop a automotive project for domestic market by XXXXXXX
Quality planning for above project
# | WBS | Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | Remarks
Concept
1 | Concept | QFD anlaysis
2 | Concept | Identify key product quality characteristics to be improved | [52 empty] | Based on external agency's published report, Warranty & TGW
3 | Concept | Agreement with R&D on past product problems to be improved
Target approval
4 | T app | Product Q target deployment
5 | T app | Reliability - veh & system wise
6 | T app | Durability - veh & system / part wise
7 | T app | Warranty - in def / 100 v & ₹ / veh
8 | T app | Fit & finish index
9 | T app | Process Q target deployment
10 | T app | Finished product rework
11 | T app | Contamination at ENG assembly
12 | T app | Assembly, machining, painting, MH rework %
13 | T app | No. of poka yoke in machining & assy processes
14 | T app | Obain approval for product & process Q targets
15 | T app | QC planning
16 | T app | Gauges planning for new parts, machining & assy processes
17 | T app | Inspection methods, equipments planning
18 | T app | Testing methods, Equipments planning
19 | T app | Plan budget for consumables | [52 empty] | (test man power, travel expenditure, no. of vehicles, fuel etc)
20 | T app | Q design review
21 | T app | Release tool design request / Purchase request | [52 empty] | (Gauges, insp & test equipments)
22 | T app | Test planning
23 | T app | Part level (Mech, Metallurgy & eleclrical)
24 | T app | System level (Mech, metallurgy & electrical)
25 | T app | Product level (performance, durability, homologation, customer usage specific)
Alpha
26 | Alpha | State of build plan
27 | Alpha | Approval for concessions
28 | Alpha | Inspect new parts
29 | Alpha | Approval for use of non conformance parts
30 | Alpha | Note problems in alpha assembly event
31 | Alpha | Raise TRF- test request forms
32 | Alpha | Part / system level testing at engine, suspension, ride & handling, NVH, homologation, Fit & finish, electrical brakes, Metallurgy labs
33 | Alpha | Vehicle level integration, durability, reliability, Safety tests
34 | Alpha | Monitor test events
35 | Alpha | Analyse test failures (test methods, acceptance criteria, part / process non conformances, design inadequacy etc)
36 | Alpha | Resolve failures
37 | Alpha | Re-test with revised parts
38 | Alpha | Weekly reports
39 | Alpha | Close TRFs
40 | Alpha | Publish report
Beta
41 | Beta | State of build plan
42 | Beta | Approval for concessions
43 | Beta | Inspect new parts / design changed parts
44 | Beta | Approval for use of non conformance parts
45 | Beta | Note status against process Q targets
46 | Beta | Note process capability of in-house machined parts
47 | Beta | Note process capability of identified assy parameters
48 | Beta | Deploy process problems to PE / OPNS teams
49 | Beta | Note problems in Beta assembly event
50 | Beta | Note problems on fit & finish index
51 | Beta | Deploy fit & finish index problems to concerned function
52 | Beta | Raise TRF- test request forms
53 | Beta | Part / system level testing at engine, suspension, ride & handling, NVH, homologation, Fit & finish, electrical brakes, Metallurgy labs
54 | Beta | Vehicle level integration, durability, reliability, Safety tests
55 | Beta | Monitor test events
56 | Beta | Analyse test failures (test methods, acceptance criteria, part / process non conformances, design inadequacy etc)
57 | Beta | Resolve failures
58 | Beta | Re-test with revised parts
59 | Beta | Weekly reporting / escalations
60 | Beta | Release Beta reports
61 | Beta | Complete PPAP audit for in house parts / processes
Pilot
62 | Pilot | Complete PPAP audits for Suppliers parts
63 | Pilot | State of build plan
64 | Pilot | Approval for concessions
65 | Pilot | Inspect new parts / design changed parts
66 | Pilot | Approval for use of non conformance parts
67 | Pilot | Note problems during build events
68 | Pilot | Note problems for vehicle acceptance in pilot production
69 | Pilot | Resolve problems for vehicle acceptance
70 | Pilot | Montor process Q status
71 | Pilot | Conduct key tests - homologation etc
72 | Pilot | Resolve product / process / part issues
73 | Pilot | Continue production
SOP
74 | SOP | Monitor complaints from service
75 | SOP | Monitor custoemr feedback
76 | SOP | Monitor customer complaints
77 | SOP | Document product / process learning
78 | SOP | Hand over to Supplier Quality

## Excercise 3 Test metric
Group 5: | Ranjit Phaltane, Souren Laha, Siddhant, Thiyagarajan, Roshan, Ramcharit
Project objective: Develop a automotive project for domestic market by XXXXXXX
Test Metric for above project
1 | XXXX Beta: test plan status
| Plan | 100
| Completed | 48
| Passed | 30
| Failed | 18
| Under progress | 17
| Test to be started | 0
| Waiting for parts | 2
| Retests to be planned | 1
| Retests passed | 0
2 | Lab wise test status | Planned | Completed | Passed | Failed | Under Progress | Test to be started | Waiting for parts | Retest Planned | Retest Passed
1 | Engine lab (Performance) | 8 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | 0
2 | Vehicle lab (Homologation) | 18 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
3 | Mechanical lab (Part / system/ Durabillity / Reliability) | 18 | 8 | 7 | 1 | 4 | 0 | 0 | 0 | 0
4 | Electrical lab (Perf / Sys / Part) | 41 | 23 | 20 | 3 | 6 | 0 | 2 | 0 | 0
5 | Product testing (Usage, durability etc) | 15 | 10 | 1 | 9 | 1 | 0 | 0 | 1 | 0
3 | Problems status : stage of problem vs severity |  |  | (Status on a particular day of test schedule; Ideally for all problems- solutions should be implemented)
| Severity Stage | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
3.1 | Registration | (Status on a particular day of test schedule; Ideally for all problems- solutions should be implemented) 10: 0
3.2 | Assessment | (Status on a particular day of test schedule; Ideally for all problems- solutions should be implemented) 10: 0
3.3 | Accept | 1 |  | 1 | 5 | 8 | 3 |  |  |  | 18
3.4 | Assign problem to concerned | (Status on a particular day of test schedule; Ideally for all problems- solutions should be implemented) 3: 1; (Status on a particular day of test schedule; Ideally for all problems- solutions should be implemented) 5: 1; (Status on a particular day of test schedule; Ideally for all problems- solutions should be implemented) 10: 2
3.5 | Immediate countermeasure | bar: (Status on a particular day of test schedule; Ideally for all problems- solutions should be implemented) 5; (Status on a particular day of test schedule; Ideally for all problems- solutions should be implemented) 10
3.6 | Root cause analysis |  |  | 1 | 1 | 6 | 2 | 1 |  |  | 11
3.7 | Solution development |  |  | 1 | 6 | 3 | 6 | 1 |  |  | 17
3.8 | Solution implementation |  | 2 | 1 | 8 | 4 | 7 | 2 |  |  | 24
3.9 | Problem resolution confirmation |  | 1 | 1 |  | 10 | 13 | 3 |  |  | 28

## Excercise 4 Communication plan
Group 5: | Ranjit Phaltane, Souren Laha, Siddhant, Thiyagarajan, Roshan, Ramcharit
Project title: | Delivery of XXX project (automotive product) in domestic market
Project Manager | ABC
Executive Sponsor | HOD, NPD
Principal stakeholder | CEO, HOD Sales, Mktg, R&D, MFG, QA & Service
Deliverable info (What) | Recipients (Who) | Delivery methods (How) | Schedule (when) | Responsible (Owner)
Project status | Project team, R&D & NPD functional heads & resp. NPD memebers | Project planning S/W, SAP PLM, Daily flow meetings | Every week day 9:30 -10 am others - accessible all time | Project planner Project team
Minutes | Project team, R&D NPD fun heads & resp. memebers | Email, project review meetings | Weekly | Project planner, Project Manager
Project weekly report & Escalations | HOD-NPD & NPD functional heads | MS powerpoint | Weekly | Project Manager
Project weekly review | President NPD, HOD-NPD, R&D, Style | Presentation- meeting in person or MS teams meeting | Weekly | Project Manager
Management project review | CEO, HODs of NPD, R&D, MFG, QA, Service, Mktg, FIN | Presentation & meeting in person or MS teams meeting | Monthly (1st Friday of month) | Program Manager
Project risk | Management review office, Project team, R&D NPD fucntional heads | Live- risk document -shared through LAN | Bi-weekly | Project Manager
Management design review (gate review) | NPD Cluster HODs | Presentation & meeting in person or MS teams meeting | Based on project schedule (~ once in quarter) | Project Manager
Audit (Q governance) | Project team | Project plannining S/W, SAP PLM, Management deisgn review, Risk register | Before Alpha or Beta test event; Before pilot production | Project team