## Group 9
Group 9 Assignment. Vipin, Dinesh, Abhinav, Surajit, Anand, Pulkit, Krishna Professor: Sir Chaitanya Sabne

## Balance Score Sheet
Scorecard | Perspective | Objective | Measure | Target | Initiatives
Scorecard Name | Financial | Revenue to be earned from the project | Earn atleast 10% profit from the project | Complete all the work packages within 90% of estimated Cost | 1. All work packages to be awarded to subvendor at 85% of the package Cost estimated
2. Contigency of 5% of project cost to be kept as reserve for any unknown risk
|  |  |  | 100% use of Resources deployed | To ensure better monitoring of resource utilisation, introduce time sheet and T&P utilisation sheet to be filled by each Supervisor everyday to monitor utilisation of manpower deployed and Tools and plants for each work package with respect to planned utilisation as estimated in Resource Management plan
|  | Maintain Healthy Cash flow |  | CPI (Cost Performance Index )is more than 1 | Encourage employees to implement innovative cost saving measures
|  |  | Maintain positive Cash flow through out the project cycle | Adhere to the budgeted cash flow for each month, quarter and year | Proactive Billing- Produce bill to customer immediately after completion of deliverables and do rigorous follow up with Customer for bill payment.
Maintain good rapport with customer for immediate payment for bills submitted
Make an agreement with Sub vendor or Sub contractor that payment for the work carried out shall be subject to payment of bill from Customer. This will ensure all Sub vendors and contractors ensure quality job to the satisfaction of Customer
| Customer | Collaborate with Customer and ensure Customer Satisfaction with better service and Project Delivery | Ensure Customer satisfaction certificate at each delivery closeout stage | Customer complaints are quickly addressed to the satisfaction of Customer | Maintain a register of issues raised by Customer and monitor that issue is addressed promptly and Pending issues are to be highlighted in every weekly review of project with all internal stake holders
|  |  |  | Deliverables are completed with Customer acceptance as per deadline | Use of latest scientific Project management tool for planning, execution and monitoring of Project and deployment of Reliable vendors, Contractors and skilled and experience team members in the project.
|  | Ensure Customer satisfaction meeting Customer Goal of making Jai Mahal a attractive Tourist spot | Increased attractiveness of the Jai Mahal | Ensure Jai Mahal water is cleaned and surrounding is made attractive with increase of Tourist footfall | Employ experts for study and implement the expert opinion for making attractiveness of the Jai Mahal as Tourist spot to increase footfall
|  |  |  | Increase in Migratory Birds arrival at Jai Mahal due to Bird nesting | Take suggestion of bird watchers and implement their suggestion to ensure increased number of Migratory bird arrival at Jai Mahal
| Internal | Strictly adhere to Project Deadline | All Project Deliverables are on time with Customer acceptance | Monthly planned Project Target are met in term of delivery | Selection and shortlisting of all Sub vendors and Contractors on the basis of their past record on timely delivery and quality of delivery.
Selection of skilled, committed and experienced Project team members with customer satisfaction centric attitude to ensure Project is completed in time
Use of latest Project management Tools and techniques for developing better Project plan, Schedule management and Cost management
|  | Ensure Effectiveness Cost Management | Actual Cost incurred is less than budgeted cost | Ensure cost optimisation to save 10% in each work packages | Brain storm and implement cost saving measures to optimise cost of each work package
Declare incentive to team members based on cost saved with respect to planned budget
|  | Ensure High Quality of Job in Project | Adhering to Safety and Quality Plan for the project with project aim of beautification of tourist spot | Better Safety parameter in term of no accident/failure per million hours | Review safety standards being followed by all Contractors and Sub Vendors and implement strict penalty for any violation in standard with regular safety audit
|  |  |  | zero quality related complaints from Customer | Adhere to approved Quality management plan and quickly address and customer quality related complaint with full satisfaction of Customer
|  |  |  | Ensuring Jai Mahal water cleaning with dredging of the Pond without affecting the fish life | Implementation of technology acquired from the best in the world for maintaining BOD in water as per recommendation.
|  |  |  | Increase of Migratory birds to the Jai Mahal Bird nesting | employ a bird watcher and consultant to implement the suggestions for making bird nest to attract Migratory bird to attract tourist foot fall
|  | Ensure Proactive Cash payment from Customer | Adhere to planned billing cycle | No bill pending with Customer for more than a week time | Proactive billing based on the progress of Project and linking receipt of payment from Client to payment of Sub vendors and Sub Contractors
| Learning & Growth | Continuously improve team members skill and competency | Team members are provided with regular Training and skill | At least one external training and two inhouse training to be provided to each of the team member to increase their skill interim of project planning, safety awareness, Quality awareness, Customer satisfaction | Team members are selected based on their skill to impart higher skill training on Project Management, Engineering skill with focus on cost optimisation, Quality Standards and best safety practices
|  | Suppliers and sub vendors made Quality driven and Customer satisfaction oriented | Suppliers and sub vendors are subjected to periodic audit on safety and quality practices followed by them | Weekly, Monthly audit of safety and Quality related non conformance by Sub vendors, Suppliers, Contractors and enforcing strict adherence to Quality and safety policy at Project site | Training imparted to each manpower deployed by Sub Vendor or Contractor on importance of Quality and Safety and making the aware of safety and Quality policy before induction at site

## Quality Plan
| Work Description | Quality Activity
1 | Approval from regulatory bodies | Standard | Time/ Schedule | Evaluation/Method | Responsibility
1.1 | Approval of project budget | Budgeted Cost | Before beginning of execution work | Project Management Plan | Project Manager
1.2 | Approval of waste disposal | Specified location |  | Project Management Plan | Project Manager
1.3 | Approval of drainage layout | Specified rout |  | Project Management Plan | Project Manager
1.4 | Approval for bidding Document | NA |  | Organizational Process Asset | Finance Manager | Legend: RFP - Request For Proposal BOM - Bill Of Materials BOQ - Bill Of Quantity PO - Purchase Order BOD - Biological Oxygen Demand
2 | Proposal floating & finalization
2.1 | Advertisement for RFP | To reach out the competent contractor | Once project is approved | Digital Media & Newspaper | Purchase & Finance Manager
2.2 | Selection of competent RFP | To select the competent contractor | After RFP floating | Cost, quality & capability | Purchase & Finance Manager
2.3 | Contract Sign off | Type of contract | After RFP finalization | Cost, quality & delivery time | Purchase/ Finance Manager & contractor
3 | Construction of Drainage
3.1 | Preparation & finalization of BOM | Type of required resources | After project approval | Listing out the required resources | Project Manager & team
3.2 | Preparation & finalization of BOQ | Quantity of resource | After project approval | Listing out the required resources | Project Manager & team
3.3 | Floating of PO | Type of contract | After contract signed off | Resource availability, cost & delivery on time | Purchase/ Finance Manager & contractor
4 | Cleaning of Lake
4.1 | Aquatic animals relocation | Cleaning | Completion of drainage work | Zero life loss of aquatic animals | Contractor & team
4.2 | Dredging |  | After aquatic animals relocation | 100% removal of silt from lake bed | Contractor & team
4.3 | Biological treatment of Lake |  | Post Dredging Work | BOD level must be <15 | Contractor & team

## Communication Plan
S.No. | Discussion point | Responsibility | Frequency | Priority | Medium of communication | Receiver ( Government/Public/ Project Team)
1 | Project Kick-off | Project manager | Initiation of Project | High | Email, Formal meeting with team, Display Board | Project team
2 | Project Engineering documentation | Project manager | Once | High | Email, Meeting | Government Approval
3 | On-site project progress | Site Manager | Weekly | High | Email, Meeting | Project Lead, Project Manager
4 | Safety Review | Safety Manager | Weekly | High | Email, Meeting | Site Manager, Project Lead, Project Manager
5 | Quality Review | Quality Manager | Weekly | High | Email, Meeting | Project Manager, Site Manager
6 | Risk Register Review | Project Manager | Half-Yearly | High | Email, Meeting | Government
7 | Change Requests | Government | Quarterly | High | Email, Meeting | Project Manager, Site Manager
8 | Budget Review | Site Manager | Monthly | High | Email, Meeting | Project Manager, Government
9 | Meeting with vendors | Procurement Manager | Monthly | High | Email, meeting | Vendors
10 | Review of the project status with client | Project manager | Quarterly | High | Email , Meeting | Government
11 | Stakeholder | Project manager | Monthly | High | Meeting | Government
12 | Project Levels Skills Gap Assessment | HR Manager | Quarterly | Medium | Email , Meeting | Project Manager

## Test Metrics
Sr No. | Testing Metric | Data retrieved | Failed Test cases Analysis
1 | No. of requirements | 6 | Failure Reason | No. of Test failed
2 | Avg. No. of Test cases | 20 | Pipeline Channel layout | 2
3 | Total No. of Test cases | 120 | Leakage in pipeline | 3
4 | Total No. of Test cases Executed | 100 | Fountain Assembly problem | 2
5 | No. of Test cases Passed | 65 | BOD level Standard | 3
6 | No. of Test cases Failed | 30 | Chemical composition of CV Technology | 10
7 | No. of Test cases Blocked | 5 | Water Report | 8
8 | No. of Test cases unexecuted | 20 | Soil report for plantation | 2
9 | Total No. of defects identified | 15 | Total | 30
10 | Critical defects count | 2
11 | High severity defects count | 4
12 | Medium severity defects count | 3
13 | Low severity defects Count | 6
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.