## Group 10
Group 10
Tushar Mhamunkar
Saurabh Singh
Gurmeet Singh Manik
Naushaba Khan
Anshu Rawal
Ravi Francis
Vishal Mukherjee
Assignment topics
1. Quality Management Plan including testing activities and Metrics | Project - IT - Monthly sprint in a product Organisation
2. Balanced Scorecard | Project - Jal Mahal
3. communication Management Plan | Project - Jal Mahal
4. Project Planning | Project - Jal Mahal

## Quality Management Plan - Activ
Quality Management Plan - Activities & Metrics
Activities & Quality Management in an IT Product based organization following a 1 month Sprint cycle
Assumptions | 1. Product backlog (Regularly) is continuously enhanced by Product team to include new features, customer bugs, enahancements (collectively called as stories) 2. a new sprint starts on Sprint planning day (denoted by N) 3. A typical sprint lasts for 1 month
Note | Following plan contains the blended version of SDLC implemented in hybrid (agile + waterfall) methodology
WBS | Activity | start date (N) | end date (N+30) | Comments
Sprint 1 Initiation
Requirement analysis
| collect & update Requirements in stories | N-7 | N | Starts before start of sprint
| Priortizing the stories for sprint | N-2 | N
| Sprint Planning | N | N
| Backlog grooming | N | N+2
| Defining the sprint goals | N | N+2
| Identifying the Developer and QA | N | N
| Requirement phase completed |  |  | Milestone
Development
| Development | N | N+7
| Unit Testing | N | N+7
| code Reviews | N+7 | N+10
| Development Phase completed |  |  | Milestone
Quality Assurance | Test Planning | N | N+7 | Testing begins in parallel with Development
| Test Plan Reviews | N+7 | N+10
| System Testing | N+10 | N+17
| Manual Regression Testing | N+17 | N+19
| Automation Regression Testing | N+19 | N+21
| Non Functional Testing - Accessibility and UI | N+17 | N+18
| Bug Fixes & Re-testing | N+10 | N+21 | QC Ongoing activity during testing
| Running the checklists | N+19 | N+21
| QA Sign-off | N+18 | N+21
| Testing Phase completed |  |  | Milestone
Product Demo
| sprint Demo | N+22 | N+22
| Product Owner Sign Off | N+22 | N+23
| Executing the Definiation of Done (DoD) checklist | N+22 | N+23
| Ready for RC Phase |  |  | Milestone
Release Candidate Build Verification
| Creating a RC build | N+22 | N+23
| system Integration Testing | N+23 | N+25
| Automation Testing | N+23 | N+25
| Security Testing | N+23 | N+25
| Performance Testing | N+23 | N+25
| Cross Platform Testing | N+23 | N+25
| SIT checklist execution | N+25 | N+25
| System Integration Testing completion | N+25
| Deployment into Staging Environment | N+25 | N+25
| UAT Testing | N+25 | N+27
| RC completed, Ready for Go-Live |  |  | Milestone
Go-Live
| Deployment into Production Environment | N+28 | N+28
| Post Production Testing | N+28 | N+28
| Production Deployment completed |  |  | Milestone
Closure
| sprint Closure activities | N+29 | N+29
| Sprint Retrospective and Documenting lessons learned | N+30 | N+30
| Sprint 1 completed |  |  | Milestone
Sprint 2 Initiation |  | N+30
Testing Metrics
Burn down data for test Execution
1. Burn Down Chart (Testing) | Burn down Chart identifies the number of Test cases Planned vs completed over time plotted against the time remaining |  |  |  |  | Burned Down |  | Balance
[5 empty] | Day | Planned | Actual | Planned | Actual | Daily completed
| Total Requirements (A) | 3 |  |  | 0 |  |  | 800 | 800
| Approx. Scenarios drafted per requirement (B) | 5 |  |  | 1 | 90 | 61 | 710 | 739 | 61
| Approx Test cases scripted per requirement (C) | 20 |  |  | 2 | 90 | 37 | 620 | 702 | 37
| Total test cases scripted (D = A xB X C ) | 300 |  |  | 3 | 90 | 99 | 530 | 603 | 99
| Manual Regression Testing cases (E) | 500 |  |  | 4 | 90 | 104 | 440 | 499 | 104
| Total Test cases for Manual Execution (F = D +E) | 800 |  |  | 5 | 88 | 124 | 352 | 375 | 124
[5 empty] | 6 | 88 | 61 | 264 | 314 | 61
| Total number of System Testing days (7) including Manual Regression (2) | 9 |  |  | 7 | 88 | 51 | 176 | 263 | 51
| Total number of QA engineers in Scrum Team | 4 |  |  | 8 | 88 |  | 88 | 263
| Avg. number of execution per engineer/ per day (= (F/G)/H) | 22.2222 |  |  | 9 | 88 |  | 0 | 263
2. Testing Velocity | Velocity takes a mathematical approach to measure how much work a team completes on average during each sprint, comparing the actual completed tasks with the team’s estimated efforts.
| Observation |  | Testing Velocity
| As per the table on Right, A testing team of 4 members can |  | Sprint | Total number of Stories delivered | Story Size | Cumulative Story Points
| 1. Deliver ~ 5.4 stories per sprint |  |  |  | (S,M,L, XL) | S- 20 M-30 L-50 XL - 70
| 2. with cumulative Story points ~ 180 |  | 1 | 5 | 3- S 1-M 1-L | 140
|  |  | 2 | 4 | 2- S 2-M | 100
|  |  | 3 | 8 | 6- S 1- M 1- XL | 220
|  |  | 4 | 3 | 1-L 2- XL | 190
|  |  | 5 | 7 | 2- S 3-M 1-L 1- XL | 250
|  |  | Velocity | 5.4 |  | 180
3. Percentage of Automated Test Coverage | measures the percentage of test coverage achieved by automated testing
as time progresses and more tests get automated, you should expect higher test coverage and, as a result, increased software quality.
4. Code Complexity / cyclomatic complexity | It counts a number of linearly independent paths through a program’s source code.
Through this QA can determine determine the risk of unstable or error-prone code. Determining complexity lets QA evaluate how likely something is to go wrong with the feature or release
5. Escaped Defects Velocity | this counts the defects for a given release that were found after the release date by the customer in Production
Escaped Defects
| Sprint | Defects found in Production #
| sprint 1 | 4
| sprint 2 | 7
| sprint 3 | 3
| sprint 4 | 1
| sprint 5 | 2
| sprint 6 | 4
6. Defects Categorisation | This metric is used to categorise the defects found in different phase such as -
Manual testing automation Regresion Security testing Performance Testing Cross browser Testing
this can be displayed using Pareto charts
Defects Classification
| Sprint | Defects found in Production #
| Manual Testing | 82
| Automation testing | 17
| Security testing | 6
| Performance Testing | 4
| Cross Browser Testing | 11
7. Defect turnaround time | This metric is used to calculate the turnaround time taken for a defect to be closed.
this can be used to improvised the SLA of Defect fixing and retesting

## Balance Scorecard - Jal Mahal
Balance Scorecard - JalMahal Project
Objective | Customer Satisfaction | Objective | Cost Optimization and contribution to profit
Measure | Fulfill all customer acceptance criteria. | Measure | Success - Schedule Performance Index >1 Cost Performance Index > 1 Failure - Schedule Performance Index <1 Cost Performance Index < 1
Target | Project acceptance with zero punch points | Target | Increase profit by 5%
Initiative | `- Hire expert consultants - Regular meeting with customer on project progress and update | Initiative | `- Use of latest technology - Hire cheap labour - Optimize supply chain
Objective | Lake cleaning with Biological Oxygen Demand (BOD) of lake as per standards. | Objective | Deliver project before schedule
Measure | BOD < 15 | Measure | Success - SPI>1 Failure - SPI<1
Target | Develop/Import new technology to maintain BOD at desired levels for a sustainable period. | Target | Delivery of project ahead of schedule.
Initiative | `- Capital investment for R&D -Incentive for developing/importing such technology at reasonable cost. | Initiative | Planning and Engineering during the monsoon period for complete readiness to start project immediately after monsoon

## Communication Management Plan
Jal Mahal Project
Description | Frequency | Method | Audience | Owner
Name of the communication | How Often it will happen | Method of Communication | Who will receive the communication | Who is responsible
Kick-off meeting | Once | Team meeting | Project sponsor, project manager, project team | Project Manager
Initial Project Details | Once | Email / collaboration tool | Project Team | Project Manager
Project grooming and clarifications | SOS | Email / collaboration tool | Project Team | Project Manager
Project update , CR updates | SOS | Email / collaboration tool | Project Team | Project Manager
Daily Team meeting | Daily | Team meeting - in person or virtually over messaging s/w , telephonic or video conferencing | PM, Team Members | Project Manager
Daily Progress Report | Daily | Email | Customer, Project Manager, Business Head, Account Head | Site Incharge
Approval Status | Weekly | Email | Customer, Project Manager | Liason Manager
Governance Meeting | Fortnight | Meeting | Project sponsor, project manager, project team | Project Manager
Stock Register | Fortnight | Email/SharePoint | SCM, Project Manager | Material Incharge
Budget Tracker | Weekly | Email/SharePoint | Accounts, Business Head | Project Accountant
Project Risks updates | Weekly | Email / Management meeting | Risk Manager, Program Manager, Project Manager | Project Manager
Project Status | Weekly | Email/SharePoint | stakeholders | Project manager
Stakeholder Register | SOS | Email / Broadcast | Stakeholders | Project Manager
Closure meeting | Once | Team meeting | Project sponsor, project manager, project team | Project Manager

## Project Planning
Estimated Project Schdeule for construction of JAL MAHAL
Activity | Start Date | End Date
Project Start | 19/07/20 | -
Construction of channel | 2020-02-08 | 18/11/20
Dredging ( Mud Cleaning) | 25/11/20 | 31/03/21
Cleaning of lake through biological treatment | 2021-03-04 | 31/05/21
Development of nesting island | 21/08/20 | 30/08/20
Fountain installation | 2021-12-08 | 30/09/21
Introduction of fishes | 2021-05-10 | 2021-10-10
Plantation of trees | 13/08/21 | 15/10/21
Project completion | 16/10/21 | 19/11/21
Toal Estimated length of project | 15 Months
** Assuming that all approvals and procurements are in place