## Estimation and Budgeting
For Every action there is A FINANCIAL REACTION
Absolute |  | Relative |  | Survival
Profit |  | RoI |  | Cash flow
Engineered cost
Discretionary cost
Revenue |  | Investment |  | Cost
Investment is money blocked in the system
with an intention to generate more money in the future
|  | vidhi | 100000 | 200000
|  | Ravi | 10000000 | 100 cr | Free of cost
Is Ravi creating or destroying wealth
Opportunity cost of capital is what Ravi can get from RBI bonds
Two projects in the same company in two different domains of business
|  | For Eg: L and T has switch gear division |  |  |  |  | 20% | ROI
|  |  | L and T has a defence division |  |  |  | 15% | ROI
Do they compete with each other?
One dealer who is very reliable
|  | Anand Auto |  | 1000000 |  | Receivable
|  | I'll pay now |  | 950000 |  | Can Gaurav make 50000 return on 950000 investment in one month?
|  | I'll pay after a month |  | 1000000 |  | 0.052632 | 63.16%
Any cost reduction we try to do once the investment is made, is more like catching the bull by the tail
More than 90% of the lifecycle cost of a product or service is committed by the time the design is complete
| Q | Quantity
| R | Rate
| S | Specification/ Scope
| T | Time
| Quantity: | What is the resource?
How much of the resource?
| Rate: | At what rate I have committed this resource?
| Specs: | Scope, WBS
| Time | Scheuduling, duration
Estimating and Budgeting:
Difference between E and B
Types of Estimation
Cost fundas for estimation
What is the difference between Estimating and Budgeting?
Why do you need cost information in projects?
At Project Conception: |  |  |  |  | Cost Estimation:
Rough idea about the overall commitment |  |  |  |  | Undertaking our own proejct:
Rough idea about the feasibility |  |  |  |  | IF the project is viable; profitabililty, NPV/IRR
Rough idea about the funding options |  |  |  |  | What are the funding needs of the proejct
Selling projects:
Rough Order of Magnitude (ROM) |  |  |  |  | Tender preparation for Bidding
Just before Project Start: Project Planning: |  |  |  |  | Cost Budgeting
Clarity on the project execution |  |  |  |  | After Scope is defined:
Clarity on Resource allocation |  |  |  |  | Detailed plan for the resources commitment,
Clarity on sequencing of projects |  |  |  |  | resources payment, time of payment
Clarity on cash flow based on milestones |  |  |  |  | Note: WBS planning, resources planning, and Cost Budteting are iterative processes
Revisit the original assumption about the project
Detailing of Budgeted costs |  |  |  |  | Cost base line for the project
Once the project starts and execution is on: |  |  |  |  | Actual cost measurement and Cash flow requirement
To control and monitor cost |  |  |  |  | WBS level cost incurred to be compared with the Budget
To plan the cash flow for running the project |  |  |  |  | to take corrective action
To replan the resource allocation |  |  |  |  | Periodic cash requirement planning
Decision making during execution based on the current reality
Detailing of Actual costs
Financial reporting of projects
Measuring the Cost of the project for Capitalisation
Financial MIS (in the case of companies selling projects) | [5 empty] | Post mortem
Types of Estimation:
I am using the word estimation in the context of both Cost Estimation and Cost Budgeting
| Volume |  | How many kms of road I need to lay?
| Efficiency |  | How much concrete I need per km? How many masons I need per km per day?
| Price |  | At what what rate I can get concrete? At what rate I can get the mason?
Expert Opinion:
Where as an organisation I haven't done this type of project many times, I need to depend on the
expertise of a few resources , may be a consultant, or an internal resource, or ex employee
Plus: | May be accurate |  |  | Challenges: |  | Bias of the estimator
| Less time consuming |  |  |  |  | Curse of experience
| Gives a direction |  |  |  |  | Un aware of organsiational assets
Analogous Estimation:
Where as an organisation I have done a similar project, and we can take that as a reference for
estimating the project on hand
Plus: | Reliable history |  |  | Challenges: |  | Bias of selection
| Quick |  |  |  |  | Repeat the bad practices
| Internal expertise |  |  |  |  | Out of context
| Lower cost of estimation |  |  |  |  | Higher cost of error
Cost of measurement vs Cost of error
Cost of control must be lesser than the cost controlled
God is in the detail vs more analysis leads to paralysis
Parametric model:
Where as an organisation I have done multiple similar projects, and/or I have people with experience in
multiple similar projects, I can develop paratmeters of Input to output based on historical data or based on
technical estimation methods.
Plus: | More accurate during budget; & estimate |  |  |  | Challenges: |  | Possible to bring in complacency
| Faster to use | [5 empty] | Time consuming to establish
| Lower cost of error | [5 empty] | Higher cost of measurment
Bottom up Estimation:
Where during the Budgeting stage, with better clairty of the near future, we get into detailing of Activities, Resources
required, duration, and cost
More detailing, it takes time and effort to do that.
God is in the detail, but more analysis leads to paralysis
Go to the ground - Genchi Gembutsu
Plus | Accuracy |  |  |  | Challenges: |  | Time consuming
| Reliable | [5 empty] | Cost of measurement is higher
| Better planning (Budgeting stage) | [5 empty] | Cannot be done during estimation
If we have a well developed and updated parametric model in place, then the estimation and budgeting may have
almost similar numbers
What makes a valid assumption?
1 | Information source
2 | Validity period
3 | Responsibility for the Information
Apply | Okham's Razor |  | to validate assumptions
Assumption is always with reference to the context.

## Cost Basics
1 | Variable and Fixed cost
2 | Direct cost and Indirect cost
3 | Controllable and Uncontrollable costs
4 | Sunk, Opportunity, Apportioned costs
1 | Variable cost and Fixed cost: |  |  | WITH REFERENCE TO RESOURCE CONSOUMPTION, NOT PRICE
| Variable cost: |  | Cost that varies linearly with the volume of output
Eg: Raw material, Labour if paid on piece rate, Consumables if they vary with output
| Fixed cost: |  | Cost that remains more or less fixed within a relevant range of output
Eg: Wages, Rent, Deprn, etc
Assets are NOT Fixed costs - They are fixed assets
They appear in Balance sheet;
Depreciation is a fixed cost
In the case of IndiGo, is Fuel a Fixed cost or variable cost?
What is the output of Indigo: Reveune Pax Km (RPK)
Does the fuel cost vary linearly with the number of passengers?
By definition it is NOT a variable cost
Since Variable cost is called variable cost, all the other costs are dubbed fixed cost
Fixed costs too vary with multiple factors, other than volume.
What factors drive fuel cost?
Distance
Load factor
Efficiency of the engine, pilot
Tail wind
Thrust
Circling above before landing
Quality of fuel
Altitude
FOR THE PURPOSE OF PROJECT COST MANAGEMENT, THIS CLASSIFICATION has LIMITED USE
Let us redefine Variable cost an dFixed cost from a project perspective:
Variable cost is a cost incurred for USING a resource
Fixed cost is a cost incurred for HAVING a resource
We normally pay for a resource in two ways:
| 1 | For using the resource |  |  | Paying for the OUTPUT
| 2 | For having the resource |  |  | Paying for the INPUT
|  | INPUT based contract |  |  | 1 | Input based Rate Contract
[5 empty] | 2 | Intput based Lump sum Contract
|  | OUTPUT based contract |  |  | 1 | Output based Rate Contract
[5 empty] | 2 | Output based Lump sum Contract
|  | Input based Rate Contract: |  |  | Mason will be paid @ Rs.500 per day
Helper will be paid @ Rs.250 per day
Resource will be paid irrespective of the work performed.
|  | Input based Lumpsum Contract: |  |  | A team of 1 Mason + 2 Helpers for a month will be paid
Rs.18000
|  | Output based Rate Contract: |  |  | Rs.200 per running mt of the wall
Resource will be paid ONLY IF the output is generated
|  | Output based Lump sum Contr: |  |  | Rs.18000 for constructing this wall of 100 mts.
Which type of contract is better? Or when one method is better than another.
|  | Based on Financial Filter only: | [5 empty] | Governance Filter
|  |  |  | Input based |  | Output based |  | Strategic Filter
|  | Ceteris Paribus |  | (Fixed cost) |  | (Variable cost) |  | Technical Filter
|  | Volume |  | High |  | Low |  | Financial Filter
|  | Frequency |  | High |  | Low
|  | Productivity |  | High |  | Low
[5 empty] | 1600 |  | On an ave
| 1000 u | [5 empty] | Volume
[5 empty] | 200 |  | 1000
| 1 | We tend to go by only one method of engagement, whereas a bit more understanding
of V, F, P can help us to re look at our contract based on the specific project requirement
| 2 | By creating and engaging the resources fully by distributing the work load, it can create
more utilisation for the same resource; then a fixed cost contract can be profitable
Deskill to multiskill
| 3 | An extremely important pre requisite for this is a meticulous planning of load levelling
(Heijunka)
2 | Direct cost and Indirect cost |  |  | Classification based on traceability
|  | Direct cost: |  | Cost that is directly traceable to the cost object
and worth tracing (Cost of measurement is lower than the cost of error)
|  | Indirect cost: |  | Cost that is traceable to a cost object, but not worth tracing, and
cost that is not traceable to a cost object
(Cost of measurement is higher than the cost of error)
What is the cost object in a project?
What do you measure ultimately?
Cost of a WBS
Cost of a Project
|  | WBS level Direct Cost: |  |  | Costs that are directly traceable to the WBS and worth tracing
Eg: Land Clearance for site preparation
|  | Project level Direct Cost: |  |  | Costs that are directly traceable to the project, but not to a
specific WBS
Eg: Site incharge
|  | Indirect cost: |  |  | All common costs that are loaded to the project
Ctrl C Ctrl V what ever you mentioned are the uses of this classfiication of Direct cost.
More critically, WBS level Direct cost has a TENDENCY to increase when we crash a project
whereas, Project Level Direct cost has a TENDENCY to decrease when we crash a project
3 | Controllable and Uncontrollable costs
|  | Controllable event |  |  |  | Uncontrollable event
which I failed to control
Abnormal event,
Not expected to repeat
cannot influence the future cost
[6 empty] | Non recurring | Recurring
[6 empty] | We need to cover | To be covered
[6 empty] | this with | thru a variation
[6 empty] | Force majeure clause | clause
4 | Sunk, Opportunity, Apportioned costs
| Sunk cost: | Costs already incurred; this is not relevant for decision making
(Especially short term decision making)
If the traffic can bear, I'll include them in my quote; otherwise I may not consider them
| Opportunity cost: |  | Revenue loss which I would have got from another opportunity, arising due to
taking up this option
Loss of the next best alternative
Whether to crash the project duration or not?
BOT crashing to earn the revenue earlier
Free up resources to be used in another project
Early completion leading to reaching the market earlier
Early completion will get me an incentive from client
| Apportioned cost: |  | All common costs that are not traceable to any specific project directly,
but they will be loaded to the project cost
Relevant while bidding
Relevant while finalising the cost of the project for capitalisation
Irrelevant for decision making regarding the project

## EVM
We shall be constructing a Road
Length |  | 100 | kms
Duration |  | 10 | months
Cost of the project |  | 100000 |  |  |  | Budget At Completion (BAC)
Resource consumption, Cost incurrence and Project completion are linear
Every month |  | 10 | Kms
Every month |  | 10000
Jan to October is the project duration; we are in End July
Actual length of road constructed |  |  | 66 | kms
Actual cost incurred |  |  | 68350
Please analyse whether the going has been good, bad or ugly
Construction should have been |  |  | 70 | kms | 70000 | Planned Value (PV) |  | Bud Cost of Work Sch
Actual constuction |  |  | 66 | Kms | 66000 | Earned Value (EV) |  | Bud Cost of Work Performed
|  |  | 66 | kms | 68350 | Actual Cost (AC) |  | Actual Cost of Work Performed
In terms of schedule: |  |  | Schedule Variance |  | -4000 | EV-PV
In terms of cost: |  |  | Cost Variance |  | -2350 | EV-AC
| We need to complete another |  |  | 34 | kms
| We have been behind schedule to the tune of |  |  |  | -4000
| We have incurred more cost to the tune of |  |  |  | -2350
Scenario1: | Let us assume that we shall complete the balance length as per the budgeted cost and time lines
| => we shall complete the 34 kms by End October by incurring an addional cost of | [7 empty] | 34000
| This is called |  | Estimate to Complete |  |  | ETC |  |  | 34000
| The cost at completion will be |  |  | AC + ETC |  | 68350 | + 34000 |  | 102350
| This is called |  | Estimate At Completion |  |  | EAC |  |  | 102350
Two ratios that are relevant for our monitoring:
| Schedule performance index (Spi) |  |  | < 1 it is behind schedule |  |  | EV/PV | 0.94286
|  |  |  | > 1 it is ahead of schedule |  |  | You have done 94% of the work
| Cost Performance Index (Cpi) |  |  | <1 is cost over run |  |  | EV/AC | 0.96562
|  |  |  | > 1 is cost under control |  |  | For the given work you should have
incurred 97% of what you incurred now
For 1$ spent I earned work worth 97%
Scenario 1: |  | If we have to complete this by October, I need additional resources to speed up the work.
|  | More man power - > |  | 1000
|  | HO Monitoring cell -> |  | We need to visit the site more often - Three addl visits reqd. - | [5 empty] | 500
|  | Of the total 100000 |  | 40000 | Fixed cost
|  |  |  | 60000 | Variable cost
|  | Fixed cost - we shall incur |  |  | 4000 | per month
|  | Variable cost - we shall incur |  |  | 600 | per km
If these suggestions are implemented, then we can complete the project by end October.
The variable cost performance will be as per budget
(other than the additiona resources and visits needed)
|  | ETC | Incremental Variable cost for 34 kms |  |  |  | 20400
|  |  | Additional visits |  |  |  | 500
|  |  | Additonal man power |  |  |  | 1000
|  |  | Fixed Cost |  |  |  | 12000 | 3 more months
|  |  | ETC |  |  |  | 33900
|  |  | EAC | AC+ ETC |  |  | 102250
Scenario 2: |  | We shall not expedite; we will spill over to November 16th. So the additonal fixed cost for November will be 900.
Variable cost will be incurred as per plan
Fixed cost till October will be incurred as per plan
If these suggestions are implemented, then we shall complete the project by November 16th.
|  | ETC | Incremental Variable cost for 34 kms |  |  |  | 20400
|  |  | Fixed cost till October |  |  |  | 12000
|  |  | Addl Fixed cost for November |  |  |  | 900
|  |  | ETC |  |  |  | 33300
|  |  | EAC = AC+ ETC |  |  |  | 101650 | -600 | 100000
-0.6%
| Budget | 100 | Kms | VC | 600 | 60000
|  |  |  | FC pm | 4000 | 40000
100000
[5 empty] | VC | FC | Total
Construction should have been |  |  | 70 | kms | 42000 | 28000 | 70000 |  | Planned Value (PV)
Actual constuction |  |  | 66 | Kms | 39600 | 26400 | 66000 |  | Earned Value (EV) |  | What is it worth? Not what I am supposed to incur
|  |  | 66 | kms | 38940 | 29410 | 68350 |  | Actual Cost (AC)
In terms of schedule: |  |  | Schedule Variance |  | -4000 | EV-PV | The work I completed was supposed to be worth 70000; but it is worth only 66000
In terms of cost: |  |  | Cost Variance |  | 660 | EV-AC | Variable cost -> I am supposed to incur 39600; but incurred 38940 => I have saved 660 on VC
|  |  | VC |  | 660 | Favorable
|  |  | FC |  | I am supposed to incur |  | 28000 | Fixed Cost => I am supposed to incur 28000, but incurred 29410 => I spent 1410 more
[5 empty] | I incurred |  | 29410 | The work is worth (FC) 26400 (Ev) => If our project continues in the same way, there will be
[5 empty] | My over run |  | -1410 | a delay => which might cause the Fixed cost to go up as well!
What is the probable amount by which the FC will go up?
(Assuming everything is as per budget)
[7 empty] | 30 | 4000 | 10 | kms
[7 empty] | 12 | 1600 | 4 | kms
|  |  | FC | EV-PV | -1600 | Sch Variance
|  |  |  | EV-AC | -3010 | Cost Variance
|  |  |  | EV-PV (Sch) |  | -1600 | This is what we are likely to incur if the time over run spills over
|  |  |  | PV-AC |  | -1410 | This is what my cost over run is AS ON DATE.
A favourable variance need not necessarily mean, that everything is fine; It may be because a deeper malise.
Poor workmanship leading to saving in cost; but resulting in inferior output and outcome

## Evaluation of Project
Those who say "No, I don't have a finance background"
If you receive Rs.50000 to day vs you receive Rs.50000 after 3 months, which is more valuable
Today or after 3 months
Money received today is more valuable than the money which we receive later
everything else remaining constant. (Ceteris paribus)
Interest, inflation, opportunity cost, risk - all these things make it viable to get the money earlier
In the case of project, when you get the cash and when you pay the cash is very crucial in
deterimining if the project is viable or not
So for appraisal of the project, what we need to look at is the cashflows and not the profit
| I sell projects |  |  |  |  | I undertake projects for my business
| Eg: I construct bridge for my client |  |  |  |  | Eg: I construct a plant to expand my current capacity
0 | I incur some cost upfront |  |  |  | 0 to 3 | I mobilise resources
mth 1 | I receive some advance |  |  |  |  | I pay to contractors
Mth 4 to 6 | I mobilise some resources |  |  |  |  | I complete the installation
| I continue to spend on resourses |  |  |  |  | I do the trial run
mth 6 | I get some milestone payment |  |  |  |  | I build initial inventory
mth 7 to 9 | I continue to spend on resourses |  |  |  | 4 | I get cash inflow from sales realisation
Mth 10 | I get some more milestone payments |  |  |  |  | (I sell to customers, they pay later,
Mth 11-13 | I continue to spend on resourses |  |  |  |  | minus I pay to suppliers)
Mth 14 | I dehire resouces |  |  |  | 5-10 yrs | I keep getting cash inflow from sales realisation
Mth 18 | I get my final payment |  |  |  |  | I assume that I do this for a specific period
(For eg; you may consider a project life of say 7 years horizon, or
5 years horizon; and assume that you will wind up in the last year)
[5 empty] | Year 10 | Terminal cash outflows
[5 empty] | Year 10 | Terminal cash inflows
Two methods of Financial Appraisal:
Non discounting method:
Pay back period:
| Year | A | Cum CF | B | Cum CF
| 0 | -100000 | -100000 | -100000 | -100000
| 1 | 20000 | -80000 | 40000 | -60000
| 2 | 20000 | -60000 | 30000 | -30000
| 3 | 30000 | -30000 | 30000 | 0
| 4 | 30000 | 0 | 20000 | 20000
| 5 | 40000 | 40000 | 20000 | 40000
|  | 140000 |  | 140000
How fast we get our investment back?
Earlier the better
It is a quick way to understand viability (Back of the envolope working)
If the project/ product is having a shorter product life cycle.
Where obsolesence risk is higher; there pay back period is a better method
Where I am investing in Tactical capex (small investments to run by business as usual)
Discounted Cash flow method
| Year | A |  |  | B
| 0 | -100000 |  |  | -100000
| 1 | 20000 | 18035.9984 |  | 40000
| 2 | 20000 | 16264.862 |  | 30000
| 3 | 30000 | 22001.4769 |  | 30000
| 4 | 30000 | 19840.9302 |  | 20000
| 5 | 40000 | 23856.7324 |  | 20000
|  | 140000 | 100000 | 0 | 140000 | 7626.4198
| Cost of capital |  | 10.89% | IRR | 14.31%
If NPV is positive, the project is viable
Project having higher NPV is giving a better return than a project having lower NPV (Certis paribus)
IRR -Internal Rate of Return - What is the return from the project

## Exercises
Exercise 1: | Identify one resource used in your project
List the drivers of that resource usage
Eg: | Cement for concreting:
| 1 | Outer dimensions of the wall
| 2 | Usage of the wall
| 3 | Load on the wall
Measure the resource consumption in terms of
quantity, specification, efficiency, rate
Exercise 2: | Get back to any of the projects you have on hand
Consider the nature of contract you have with the service prrovider
Is it Input based or Output based
What do you think are the advantages you gain (purely financial)
by having the contract in the current way
What do you think may be the dangers you may face in the
current way of engagement