## Risk Register
Risk Category | Risk Title | Risk Description | Impact | Impact Significance | Likelihood | Likelihood Significance | Risk Score | Schedule Impact | Cost Impact | Scope Impact | Control Owner | Risk Response | Risk Action
Environmental Risk | Water Treatment | Impact to Jal Mahal structure due to water treatment | 4 | Severe | 2 | Unlikely | 10 | Delay by a month | 1 Cr | Additional restoration scope | Environmental Manager | Mitigate | Regular structure inspection by environmentalist
Environmental Risk | Public Behaviour | Ineffective public awareness drive to change public behaviour | 4 | Significant | 4 | Likely | 16 | Delay by a month | 10 Lacs | Additional awareness drives to be conducted | Environmental Manager | Transfer | Hire experts from media & marketing
Environmental Risk | Water Contamination | Water Contamination due to chemical addition | 2 | Minor | 3 | Possible | 6 | Delay by two months | 50 Lacs | Water contamination to be removed | Environmental Manager | Mitigate | Regular water testing
Schedule Risk | Environment Clearance | Delays in recieving environmental clearances | 2 | Minor | 2 | Unlikely | 4 | Delay by two weeks | Increase in Sunk cost | Additional resources to expedite permissions | Project Manager | Mitigate | Seek government support
Schedule Risk | Activity Overlaps | Multiple activities on critical path impacting schedule | 3 | Moderate | 4 | Likely | 12 | Delay by 4 months | 50 Cr | Allocation of resources towards co-ordination | Project Manager | Mitigate | Close schedule monitoring
Schedule Risk | Technology Procurement | Delays in importing CV Technology | 5 | Severe | 3 | Possible | 15 | Delay by three weeks | 10 Cr | Arranging Alternative technology for time being treatment | Project Manager | Mitigate | Seek government support to get clearances
Schedule Risk | Statutory Approvals | Delay in project approvals and permits | 5 | Severe | 3 | Possible | 15 | Delay by one week | Increase in Sunk cost | Additional resources to expedite permissions | Project Manager | Mitigate | Assign and allocate task to different teams
Financial Risk | Project Delays | Schedule delays causing cost overrun | 4 | Severe | 4 | Possible | 12 | Extended project duration | 40 Cr | Cost overruns leading to optimizing resources | Project Manager | Mitigate | Regular checks and proper planning of contingency measure to ensure performance levels are met
Financial Risk | Labour Availability | Unavailability of cheap & skilled labor leading to cost overrun | 4 | Significant | 3 | Possible | 12 | Delay by two weeks | 30 Cr | Arranging for training of semiskilled workforce | Project Manager | Mitigate | Build in cost contingencies
Financial Risk | Cash Flow Delays | Delay in Cash Flow due to client remittances | 4 | Significant | 4 | Possible | 16 | Delay by one week | Working Capital & Liquidity Crunch | Arranging for alternative finance to mitigate crunch | Project Manager | Accept | Build in cost contingencies
Operational Risk | Drainage System | Cracks in drainage pipes leading to contamination | 4 | Significant | 3 | Possible | 12 | Delay by a month | 10 Cr | Mitigating the leaks and wherever possible repairing cracks | Channel Construction Manager | Mitigate | Regular stress testing of pipes
Operational Risk | Channel Route | Roadblock in finding appropriate channel route | 5 | Moderate | 3 | Possible | 15 | Delay by two weeks | 5 Cr | Deploying advanced technologies and field experts | Channel Construction Manager | Research | Detailed study on the routing
Operational Risk | Waste Generation | Incoming waste flowing out of natural outway | 4 | Significant | 3 | Possible | 12 | Delay by three weeks | 30 Lacs | Sustainable waste collection, mitigation and disposal | Mud Cleaning Manager | Research | Prototyping on use of boulders
Compliance Risk | Water Quality | Sustaining water quality as per WHO standards | 4 | Significant | 4 | Likely | 16 | Delay by three weeks | 2 Lacs | Additional water testing activity | Compliance Manager | Mitigate | Regular water testing
Compliance Risk | Life Under Water | Ten fish species don't survive in the pond | 3 | Moderate | 3 | Possible | 9 | Delay by a month | 5 Lacs | Purchase of additional fishes and sustaining in lake | Compliance Manager | Mitigate | Select fish species which easliy adapt to all water types
Compliance Risk | Tree Plantation | Trees planted do not survive | 3 | Moderate | 3 | Possible | 9 | Delay by two weeks | 1 Lac | Purchase of additional plants and planting | Compliance Manager | Mitigate | Select fash growing and low maintainence plants

## Risk Map
Inherent Risk Heat Map
Impact | Severe | 5 | 10 | 15 | 20 | 25
| Significant | 4 | 8 | 12 | 16 | 20
| Moderate | 3 | 6 | 9 | 12 | 15
| Minor | 2 | 4 | 6 | 8 | 10
| Negligible | 1 | 2 | 3 | 4 | 5
|  | Very unlikely | Unlikely | Possible | Likely | Very likely
Likelihood