## Risk Register
Risk Assessment
Risk Category | Sub Category | Risk description | Risk Type (Known/Unknown) | Probabilty | Risk Impact | Impact on schedule | Impact on cost | Risk Ranking | Risk Level | Risk Response (Mitigation) | Risk Action (Contigency Plan) | Probabilty Impact analysis | Risk Owner
Internal | Management Risk | Project approval from the Management Change in Management | Known/Unknown | 0.1 | 0.9 | High | Low | 0.09 |  | Avoid | We will try to eliminate these risk as far as possible by effective communication to the senior management and taking management approvals before the start of the project |  | Steering Committee
| Quality Risk | Procuring good quaility of CCTV camera Maintaining the water quality of the pond to sustain aquatic life | Known/Unknown | 0.5 | 0.7 | Low | High | 0.35 |  | Mitigate | Review quality at regular intervals Ensure supply vendor for equipments like CCTV and other equipments is well defined in advance. |  | Project Manager
| Operational Risk | Delay in Supply of fountain Logistic issues in getting new fishes to the pond Plantation of trees around lake | Known/Unknown | 0.9 | 0.8 | High | Medium | 0.72 |  | Mitigate | Design Target Operating model for each of the operations. All logistic issues pertaining to water quality of pond and procurement of trees is well defined |  | Project Manager
| Resource unavailability | Non availibility of local labors Lack of skilled labor Attrition during the course of business | Known/known | 0.7 | 0.8 | High | High | 0.56 |  | Mitigate | Keep a resource tracker to plan the available resources during the course of project and plan alternatives for any unavailability. To overcome the scenario of adhoc unavailability, hire atleast 2 people more than actual in each department |  | Project Manager
| Credit risk | Funding Risk | Known/Unknown | 0.6 | 0.7 | High | Medium | 0.42 |  | Mitigate | Have appropriate credit checks and monitoring to eliminate the risk. Also create a policy and use it consistently to avoid any such risks. |  | Finance commitee, Stakeholders & PM
| Design Risk | Any major changes in the design | Unknown/Unknown | 0.4 | 0.8 | High | High | 0.32 |  | Avoid | Design risk can be avoided by capturing all potential risk elements of the design. Have right competencies at the right places of work. Plan to eliminate, reduce and effectively manage incase of a risk |  | Architect, Project Manager & Stakeholders
| Cost Risk | Cost overruns in labour contracts due to delay in project activities Cashflow or liquidity risk | Known/Unknown | 0.2 | 0.9 | High | High | 0.18 |  | Avoid | This risk can be avoided by proper project scheduling & tracking. Regular follow ups for payment with concrened public sector authorities. |  | Project Lead
| Communication risk | Improper communication with various teams | Known/Unknown | 0.5 | 0.8 | High | High | 0.4 |  | Mitigate | This risk can be mitigated by planning, managing & monitoring communation. |  | Project Manager
| New technology implimentation | Lack of experience in similar technology usage/implementation | Unknown/Unknown | 0.1 | 0.9 | High | High | 0.09 |  | Avoid | This risk can be avoided by ensuring proper training to all the engineers & support staff berfore start of the project. |  | Steering Committee
External | Awareness Risk | Public awareness about the benefits Environmental protests | Known/Known | 0.3 | 0.12 | Low | Low | 0.036 |  | Transfer | Sufficient clearence from all concerned bodies to be taken in advance and if in case such protests or Public awareness issues arises ,the Government Authorities will have to take care of such situations. |  | Project Manager
| Regulatory risk | Approval from various Govt authorities/forest department/electricity department | Known/Known | 0.5 | 0.4 | high | high | 0.2 |  | Mitigate | Risk can be lowered by following steps:- a) Hiring a consultant to liaise with Government Regulatory bodies b)Pickup Learning from such Project happened in past c)Take all Approvals in the initial phase of the project |  | Project Director
| Environment Risk | Delay due to Force majeure Damage of water species during biological treatment | Known/Unknown | 0.5 | 0.12 | High | High | 0.06 |  | Accept | a) Contingency plan to be prepared in advance for any unavoidable cirumstances like Act of God etc. b) All Forcasts on Weather/Timing of Crop cutting etc. to be taken in consideration during planning phae c)Experts Judgement on Each Phase to taken and after analysi to be considered during Operational Implementation so as to avoid any damage to nature/water bodies etc. |  | Project Director
| Legal Risk | Any major changes in the Govt policies or policies related to the project | Known/Unknown | 0.1 | 0.9 | High | High | 0.09 |  | Accept | Need to be ready for contingency plan as gov policy change need to adhere to same.Expert support should be taken for any change |  | Project Director
| Communication risk | Immproper communication with various teams | Known/Unknown | 0.3 | 0.5 | Medium | Medium | 0.15 |  | Mitigate | Communication to various Government authorities needs to be well documented Regular interation with the parties needs to be incorporated in the project plan Monitor from time to time |  | Arvind
| Sustainbility Risk | Changes after the completion of projects in coming years | Unknown/Unknown | 0.1 | 0.9 | High | High | 0.09 |  | Avoid | This risk can be avoided by ensuring proper design, without any loopholes and with required approvals. |  | Arvind
| Political Influence Risk | Change in political scenario/ Government | Unknown/Unknown | 0.1 | 0.1 | Low | Low | 0.01 |  | Mitigate | This risk can be lowered by following steps: a) By Consulting Subject Matter Expert b) Lessons Learnt from previous projects with similar issue c) Have good rapport with Government Authorities /Political so any issues that might come up, will be resolved amicably |  | Arvind

## Risk Map
Probability | Threats Risk Score = Probability * Impact
0.90 Very Likely | 0.05 | 0.09 | 0.18 | 0.38 | 0.72
0.70 Likely | 0.04 | 0.07 | 0.14 | 0.28 | 0.56
0.50 Possible | 0.03 | 0.05 | 0.1 | 0.12 | 0.4
0.30 Unlikely | 0.02 | 0.03 | 0.08 | 0.12 | 0.24
0.10 Very Unlikely | 0.01 | 0.02 | 0.03 | 0.04 | 0.08
Risk Heat Map
Probability (Likelihood) | Impact
0.90 Very Likely | 0.05 | 0.09 | 0.18 | 0.38 | 0.72
0.70 Likely | 0.04 | 0.07 | 0.14 | 0.28 | 0.56
0.50 Possible | 0.03 | 0.05 | 0.1 | 0.12 | 0.4
0.30 Unlikely | 0.02 | 0.03 | 0.08 | 0.12 | 0.24
0.10 Very Unlikely | 0.01 | 0.02 | 0.03 | 0.04 | 0.08