## Sheet1
| Risk Identification |  |  |  |  | Qualitative Rating |  |  |  |  | Risk Response
Sr. No. | Risk Category | Risk Name | Consequence | Risk Trigger | Risk Description | Schedule Impact | Cost Impact | Probability | Impact | Risk Ranking /Score | Risk Response | Action | Trigger | Risk Owner
1 | Statutory/Legal Risks | Delay in approvals from Govt Regulaory bodies | Delay in schedule | Unauthorised Chemical Selection | Approval from irrigation department for use of technology and chemicals | Yes | No | High | High | High | Mitigate | Liason strongly taking customer's support |  | PM -1
2 | Statutory/Legal Risks | Change in legal policies | Delay in schedule, have to take more approvals or documentaion | Change in Policies | Change in legal policies due to new reforms introduced recently | Yes | No | Medium | High | High | Mitigate | Liason strongly taking customer's support |  | PM
3 | Statutory/Legal Risks | Delay in approvals from Civic Bodies | Delay in schedule, Increased cost | Proposal not in line with requirements | Delay in Approval from Municipal for diversion of drain channel | Yes | Yes | High | High | High | Mitigate | Plan drainage diversion in consultation with Monicipal deptt. |  | PM
4 | Statutory/Legal Risks | Unavailability of recommended Chemicals | Delay in sarting the Chemical treatment (Schedule) | Chemical not available in Market or Authorized vendor doesn't have a stock | Unavailability of Chemicals recommended by the authorities considering the hazards | Yes | No | Low | Medium | Medium | Transfer | Take approval for other similar chemicals |  | Procurement and Legal team
5 | Execution Risks | Resource unavailibility during different phases | Delay the project schedule | Unplanned resource may causes loss of money on manpower and loss of time. | Late Onboarding of the resources and late deployment | Yes | Yes | Medium | Medium | Medium | Transfer | Involve HR and SCM during planning stage |  | Procurement and HR head
6 | Execution Risks | Change in Design Specificaions | Redesign and planning again will incur cost | Change in specification cause change in cost.Redesigning may not be accurate with time. | Change in design due to failure of Design/structure or unexplored structures | Yes | Yes | Low | High | Medium | Avoid | Design with sufficient saftey factors |  | Architect
7 | Execution Risks | Unavailability of the channels for drain diversion | Redesign the Drain and approvals for the other channel | Time loss, manpower loss & cost in redesign and procurement. | Unavailability of channel for drain diversion, uncovered in the detail surveys | Yes | Yes | Low | High | Medium | Avoid | Plan drainage diversion in consultation with Monicipal deptt. |  | Procurement team
8 | Execution Risks | Delay in supply of fountains for fitting | Can delay the work schedule for testing the fountain | Inspection team availabilty due the delay in schedule. | Delay in supply of fountains for fitting | Yes | No | Medium | Medium | Medium | Transfer | SCM Manager should plan supply ahead of schedule |  | Procurement team
9 | Execution Risks | Unavailability of Labour | Delay the project schedule | Availability of manpower. | Non-availability of local labour | Yes | No | Low | Low | Low | Transfer | Hire labour from other states |  | HR
10 | Environmental Risks | Delay due to Force Majeure | Can hold the Project activities | Natural/Non-natural calamity | Delay due to Force Majeure | Yes | Yes | Low | High | Medium | share | Seek time extension and cost revision due to delay |  | Scheduler
11 | Environmental Risks | Severe bad weather conditions | Can hold the Project activities | Can further delay the project schedule. | Inclement weather conditions | Yes | Yes | Low | Low | Low | share | Plan site activities after monsoon |  | Scheduler
12 | Environmental Risks | Damage to the marine life | Legal Action can hold the work | Can further delay the project schedule. | Damage to water species during biological treatment from the chemicals | Yes | No | Low | High | Medium | Mitigate | Precision during alternate arrangement |  | Procurment and Legal team
13 | Socio/Political Risk | Local Politicians obstruction | Can stall the Site work and arrange a protest | Poilitical vendetta | Local Politicians obstruction | Yes | Yes | Medium | Low | Low | share | Take customer support to tackle situation |  | PM
14 | Socio/Political Risk | NGO obstruction | Can stall the Site work and arrange a protest | Any harm to nature/society | NGO obstruction | Yes | No | Medium | Low | Low | share | Take customer support to tackle situation |  | PM
15 | Socio/Political Risk | Local Vendors around the site obstruction | Can stall the Site work and arrange a protest | Impact on business | Local Vendors around the site obstruction | Yes | No | High | Low | Medium | share | Take customer support to tackle situation |  | PM
16 | Finance | Budget Exceeding | Cashflow issues can stop the work | Cost overrun | Budget Exceeding | Yes | Yes | Medium | Medium | Medium | Transfer | Fund planning to keep contingency funds. |  | finance team
17 | Finance | Sub-Contractor non-performance | Delay on the milestones causing delay in schedule | Allocating different contractor can lead to further delay. | Sub-Contractor non-performance | Yes | Yes | Low | High | Medium | Mitigate | use Payment management tool |  | finance and procurement team
18 | Finance | change in currency value and import duty | Will impact the cost of import and exceed the cos incurred | Can affect the on going budget. | change in currency value and import duty, assuming the machinery to be imported | No | Yes | Low | Medium | Low | Transfer | Do a FIRM price contract or hedge currency |  | finance and Forex group
Probability Impact Matrix
|  | Probability | Impact | Risk Score
|  | High | High | High
|  | High | Medium | High
|  | High | Low | Medium
|  | Medium | High | High
|  | Medium | Medium | Medium
|  | Medium | Low | Medium
|  | Low | High | Medium
|  | Low | Medium | Low
|  | Low | Low | Low