## Risk Assignment
Project : Jal Mahal Project, Jaipur
Objective : To clean Jal Mahal lake by maintaining minimum adulteration with the aim of ensuring sustainable ecological balance and green leisure tourist spot by 2020
Total Estimated Budget : INR.1000 Cr | [6 empty] | Time Duration : 15 Months
RISK REGISTER Date : 15 April 2020
Risk Identification |  | Qualitative Rating |  |  |  | Risk Response |  | Implication of Risk
Risk | Risk Category | Probability | Impact | Risk Score | Risk Response | Risk Action Plan | Risk Owner | Schedule | Cost | Scope
External | Time consuming in liasioning with local authority | 2 | 3 | 2.5 | Transfer | 1.Appoint Liasion consultant on time. 2.Schedule target time within the project duration. 3.Take Government Assistance | Project Manager | High | Medium | High
| Land identifation for muck disposal from lake bed | 2 | 3 | 2.5 | Avoid | 1.Analyse all social activities during selection of dumping yard. 2. Work out the costing & allot budget appriorately. | Project Manager | High | High | Medium
| Political risk - change in government | 1 | 2 | 1.5 | Avoid | 1.Plan all the activities within timeframe, so that none of the items/activity missed out in schedule. 2.Keep all correspondence/communication in a proper documentation. | Project Manager | High | High | High
Internal | Process failure due to operational efficiencies and Technology | 3 | 2 | 2.5 | Avoid | 1. Prepare and get approve all method statements by third party consultants before execution. 2. Make clear SOP for all the scope of works | Construction/Facility Manager | Low | High | Medium
| Inequitable hiring practices - skilled labor | 2 | 3 | 2.5 | Avoid | 1. Identify proper team for resources mobilisation. 2. Utilise the tool box talk & induction to ensure skill level of all resources. | HR | High | Medium | Medium
| Control on data integrity | 3 | 3 | 3 | Mitigate | 1. Ensure to store all the data's of project in a safer way, with controlled copies 2. Re-check the site data's & information twice before approving the same. | Project Manager | Low | High | High
Technical | Deploying of the Imported technology (CV technology) | 3 | 3 | 3 | Mitigate | 1. Plan long lead procurement items within project schdule. 2. Make sure the specificaction & details are properly vetted before placing order. | Project Manager | High | High | Medium
Technical | Consistency in arriving water & soil quality during testing | 3 | 3 | 3 | Mitigate | 1. Project Quality plan shall be detailed with frequency & method of testing. 2. Interim process check list with assurance & control, to achieve quality. | Construction Manager | High | High | Medium
Technical | Diverting existing city drain | 4 | 4 | 4 | Mitigate | 1. Prepare proper design with all existing details of drain, to implement the diversion plan. 2. Before execution, check for alternates sources for diverting/storage of sewage flow. | Project/ Construction Manager | High | High | High
Finances | No proper specification leads to increase in budget | 3 | 4 | 3.5 | Mitigate | 1. Conduct brainstorming session with tender team to make sure the detail specification are understood and budget provision is done. | Project/Finance Manager | Medium | High | High
Finances | Currency rate for imported technology | 4 | 4 | 4 | Mitigate | 1. Allocation of budget shall be done inline with the provision of currency fluctation. | Project/Finance Manager | Low | High | High
Finances | Cashflow consistency - can't deliver on time (revenue loss) | 3 | 3 | 3 | Mitigate | 1.Understand cash flow of the project from the day one of the project. 2.Make sure project is not affected due to shortfall in cash flow. | Account Manager | High | High | Medium
Unforeseeable | Risk of Health Worker | 3 | 4 | 3.5 | Mitigate | 1.Maintain good healthy & hygenic condtion in all areas of the project. 2. Frequent visits shall be done to implement healthy condtion of the workers | Project Manager | High | High | Medium
Unforeseeable | Climatic impact - Heavy rainfall | 1 | 4 | 2.5 | Avoid | 1. Understand the climatic condition with statistical data to pre-plan the activities during monsoon. 2. Check for alternate method for execution during monsoon season. | Project Team | High | High | Medium
Unforeseeable | Panademic - Covid-19 | 1 | 4 | 2.5 | Avoid | 1. Always check, to understand any panademic situatoin across globe and make readiness to control the same. | Government | High | Medium | Medium
Project Team - Group 7
|  | Likelihood | [5 empty] | Atinder
|  | 1 | 2 | 3 | 4 | 5 |  | Stephen
Impact | 5 | Medium | Medium | High | High | High |  | Gaurav
| 4 | Low | Medium | Medium | High | High |  | Gopala Krishnan
| 3 | Low | Medium | Medium | Medium | High
| 2 | Low | Medium | Medium | Medium | Medium
| 1 | Low | Low | Low | Low | Low