## Sheet1
For Every action there is A FINANCIAL REACTION
Absolute |  | Relative |  | Survival
Profit |  | RoI |  | Cash flow
Engineered cost
Discretionary cost
Revenue |  | Investment |  | Cost
Investment is money blocked in the system
with an intention to generate more money in the future
|  | vidhi | 100000 | 200000
|  | Ravi | 10000000 | 100 cr | Free of cost
Is Ravi creating or destroying wealth
Opportunity cost of capital is what Ravi can get from RBI bonds
Two projects in the same company in two different domains of business
|  | For Eg: L and T has switch gear division |  |  |  |  | 20% | ROI
|  |  | L and T has a defence division |  |  |  | 15% | ROI
Do they compete with each other?
One dealer who is very reliable
|  | Anand Auto |  | 1000000 |  | Receivable
|  | I'll pay now |  | 950000 |  | Can Gaurav make 50000 return on 950000 investment in one month?
|  | I'll pay after a month |  | 1000000 |  | 0.052632 | 63.16%
Any cost reduction we try to do once the investment is made, is more like catching the bull by the tail
More than 90% of the lifecycle cost of a product or service is committed by the time the design is complete
| Q | Quantity
| R | Rate
| S | Specification/ Scope
| T | Time
| Quantity: | What is the resource?
How much of the resource?
| Rate: | At what rate I have committed this resource?
| Specs: | Scope, WBS
| Time | Scheuduling, duration
Estimating and Budgeting:
Difference between E and B
Types of Estimation
Cost fundas for estimation
What is the difference between Estimating and Budgeting?
Why do you need cost information in projects?
At Project Conception: |  |  |  |  | Cost Estimation:
Rough idea about the overall commitment |  |  |  |  | Undertaking our own proejct:
Rough idea about the feasibility |  |  |  |  | IF the project is viable; profitabililty, NPV/IRR
Rough idea about the funding options |  |  |  |  | What are the funding needs of the proejct
Selling projects:
Rough Order of Magnitude (ROM) |  |  |  |  | Tender preparation for Bidding
Just before Project Start: Project Planning: |  |  |  |  | Cost Budgeting
Clarity on the project execution |  |  |  |  | After Scope is defined:
Clarity on Resource allocation |  |  |  |  | Detailed plan for the resources commitment,
Clarity on sequencing of projects |  |  |  |  | resources payment, time of payment
Clarity on cash flow based on milestones |  |  |  |  | Note: WBS planning, resources planning, and Cost Budteting are iterative processes
Revisit the original assumption about the project
Detailing of Budgeted costs |  |  |  |  | Cost base line for the project
Once the project starts and execution is on: |  |  |  |  | Actual cost measurement and Cash flow requirement
To control and monitor cost |  |  |  |  | WBS level cost incurred to be compared with the Budget
To plan the cash flow for running the project |  |  |  |  | to take corrective action
To replan the resource allocation |  |  |  |  | Periodic cash requirement planning
Decision making during execution based on the current reality
Detailing of Actual costs
Financial reporting of projects
Measuring the Cost of the project for Capitalisation
Financial MIS (in the case of companies selling projects) | [5 empty] | Post mortem
Types of Estimation:
I am using the word estimation in the context of both Cost Estimation and Cost Budgeting
| Volume |  | How many kms of road I need to lay?
| Efficiency |  | How much concrete I need per km? How many masons I need per km per day?
| Price |  | At what what rate I can get concrete? At what rate I can get the mason?
Expert Opinion:
Where as an organisation I haven't done this type of project many times, I need to depend on the
expertise of a few resources , may be a consultant, or an internal resource, or ex employee
Plus: | May be accurate |  |  | Challenges: |  | Bias of the estimator
| Less time consuming |  |  |  |  | Curse of experience
| Gives a direction |  |  |  |  | Un aware of organsiational assets
Analogous Estimation:
Where as an organisation I have done a similar project, and we can take that as a reference for
estimating the project on hand
Plus: | Reliable history |  |  | Challenges: |  | Bias of selection
| Quick |  |  |  |  | Repeat the bad practices
| Internal expertise |  |  |  |  | Out of context
| Lower cost of estimation |  |  |  |  | Higher cost of error
Cost of measurement vs Cost of error
Cost of control must be lesser than the cost controlled
God is in the detail vs more analysis leads to paralysis
Parametric model:
Where as an organisation I have done multiple similar projects, and/or I have people with experience in
multiple similar projects, I can develop paratmeters of Input to output based on historical data or based on
technical estimation methods.
Plus: | More accurate during budget; & estimate |  |  |  | Challenges: |  | Possible to bring in complacency
| Faster to use | [5 empty] | Time consuming to establish
| Lower cost of error | [5 empty] | Higher cost of measurment
Stay at home; stay safe

## Sheet2
Identify one resource used in your project
List the drivers of that resource usage
Eg: | Cement for concreting:
| 1 | Outer dimensions of the wall
| 2 | Usage of the wall
| 3 | Load on the wall
Measure the resource consumption in terms of
quantity, specification, efficiency, rate