## Communications Guide
Communications Guide
Introduction | The Communication Plan contains communications activities and events for all internal and external stakeholders impacted by the project
Timing | The communications Plan should be developed during the Planning, Analysis and Design Phase of PMLC
Communication Plan | The Communications Plan outlines project key messages, branding and visual identity considerations, stakeholder needs, and planned communications events and activities.
Messaging | Key messages are the three or four most important statements about a project the team wishes to share with stakeholders. They should communicate both key facts and motive. Depending on the project, it may be important to both repeat some key messages over the life of the project, and introduce new messages as the project evolves.
Executive Staff | Recommend use External Relations and have Executive Sponsor Approval
Faculty | Recommend use External Relations and have approvals from Executive Sponsor, School Dean and/or Provost's Office
Staff | Recommend use External Relations and have approval from Executive Sponsor
Students | Recommend use External Relations and have approvals from Executive Sponsor and Provost's Office
External Stakeholders | Recommend use External Relations and have Executive Sponsor Approval
Messaging Medium | Some types of Communication have specific sign-off and requirements, see infomail as an example
Infomail Protocol and Guidelines | Provides an overview of protocols and guidelines as related to distribution of mass emails to University students, faculty and staff. Lead time, required sign-offs, and general information is in this guide
Branding and Visual Identity | All branding and visual identity must conform to the GW standards. Contact External Relations for guidelines.
Budget | ALL communications developed are constrained by the communications budget. As an example, If the project sponsor plans to communicate via printed materials using the USPS, the PM must contact external relations to get quotes for the printed material and related expenses. The lead time for this varies by the type of printed material.

## Communications Sample Entries
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Audience | Reviewer | Faculty / Staff / Student | Owner
1
| Name of the Communications Piece | Medium | Delivery Date | Frequency | Briefly describe the content of the communication piece | Person(s) who will receive the communication | Person(s) who will review and approve the communications piece | Faculty/Staff/Student | Person(s) responsible for document
| Examples: | Examples: | Examples: | Examples: | Examples: | Examples: | Examples: | Examples: | Examples:
| Reminder emails to Finance Staff | email | on-going | daily | design logo for iBuy Travel and Expense/Pcard | Finance Directors | External Relations | Faculty | External Relations - Joe
| Letter to Retirees re: benefit changes in 2012 | USPS Printed Letter | specify Date | weekly |  | All GW Employees | Excutive Sponsor | Student | Rebecca
| email to Executive Staff | 4 color Process Print |  | one-time |  | Retirees | Provost's Office | Staff | UWS (University Web Services)
| email to School of Business Faculty | Flyer |  | quarterly |  | Deans | Deans |  | IT Communications
| Memo to Faculty | meeting |  | yearly |  | Executive Staff | Executive Staff |  | FSS
|  | logo |  | bi-monthly |  | Faculty | Banner Steering Committee
|  | website |  |  |  | Students
|  | survey |  |  |  | Parents
|  | promotional piece |  |  |  | School of Nursing
|  | campus mail |  |  |  | VSTC Campus
|  | infomail |  |  |  | FB Campus
|  | GW Today |  |  |  | IT Help Desk
|  | Advertising |  |  |  | Banner Executive Committee
|  | phone |  |  |  | EAS Users
|  | training session |  |  |  | myGW Users
|  | memo |  |  |  | GWEB Users
meeting
ITSM Ticket

## Banner Point Release Project
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Audience | Reviewer | Owner
1 | Project Team Communication | Meeting | Ongoing | Weekly | Weekly IT status meeting to discuss schedule, communications, actions, risks & issues | IT Project Team | Dori Sobhani | Dori
2 | Banner Steering Committee Communication | Meeting | Ongoing | Bi-Weekly | Bi-Weekly status meetings to discuss schedule, communications, actions, risks & issues with impacted user groups | Banner Steering Committee | Dori Sobhani | Dori
3 | Banner Executive Committee (BEC) | Meeting | Ongoing | As Needed | Phase Gate Reviews to review project status and deliverables and to get approval to move forward in the Project Management Life Cycle | Banner Executive Committee | Carrie Bilko | Dori
4 | Executive Sponsor Communication (BEC) | Email | Ongoing | Monthly | Monthly executive overview of the project progress | Banner Executive Committee | Carrie Bilko | Dori
5 | Banner Advisory Committee (BAC) | Meeting | Ongoing | Monthly | communicate project updates | Banner Community | Carrie Bilko | Dori
6 | Entry for Change Control Calendar | ITSM ticket | 2013-10-29 | One-time | CAB for Change Control Calendar | IT Help Desk | Change Control Board | Dinesh
7 | GWEB Posting for Pending Downtime for upcoming Release | GWEB Splash page | 2013-11-11 | One-time | Load alert notice of downtime to splash page two weeks prior to release. Leave notice up until release is complete. | GWEB Users | Banner Steering Committee | Mark
8 | Downtime Communication Notice | email | 11/11/2013 11/18/2013 11/22/2013 | Three Times | Send email notification of Banner outage for the release three times. One notice two weeks ahead and two notices week of release. | Staff, Faculty and Students | Banner Steering Committee | IT Communications
9 | EAS Communication | email | 2013-11-18 | One-time | Alert notice of downtime for upgrade on 11/23/13 (5 day notice) | EAS Users | Banner Steering Committee | FSS c/o Anna de Lapparent
10 | Portal Downtime Upgrade Notice | myGW | 2013-11-23 | One-time | When users click on impacted Banner links from myGW, display page alerting users that system is unavailable due to planned upgrade. | myGW Users | Banner Steering Committee | UWS (Andy and Kavi)
11 | Cut Over Communication | Email | 2013-11-23 | One-time | Project status updates through out launch weekend. | IT Project Team, BEC & Banner Steering Committee | Carrie Bilko | Dori
SAMPLE
This is a sample of a Communications Matrix used for a real project.

## Merit Project Communications
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Audience | Reviewer | Faculty / Staff | Owner
1 | Project Team Communication | Meeting | Ongoing | Weekly | Weekly status meeting to discuss schedule, communications, actions, risks & issues | Project Team | Louis Lemieux | Staff | Adam
2a | Executive Sponsor Communication | PPT | Ongoing | Weekly | Weekly status report to executive sponsors for overview of the project progress | Executive Sponsors - Louis Lemieux & Vanessa Rose | Bruce Pankey, Michelle Wiles | Staff | Adam
2b | Executive Sponsor Communication | Meeting | Ongoing | Monthly | Monthly executive overview of the project progress | Executive Sponsors - Louis Lemieux & Vanessa Rose | Bruce Pankey, Michelle Wiles | Staff | Adam
3 | FORMAL: Merit percentage notification, range notification, basic merit guidelines (Provost, Sr Vice Provosts, VPs) | Letter | 2010-09-10 | One-time |  | To VPs, Provost, AND Sr. Provost | Lou Katz | Staff | Michelle
4 | Merit Liaison & FDs roles & responsibility | Email | 2010-09-13 | One-time | Create list of responsibilities for merit liaisons (e.g. communicate appropriate information to supevisors, dept heads, AVP's etc.) | Merit Liaisons & all FDs | Louis Lemieux | Staff | Michelle
5 | Communication to departments regarding grade minimums. | Email | 2010-09-15 | One-time | Will include instructions on ways to notify employees. | Merit liaisons | Louis Lemieux | Staff | Michelle
6 | FORMAL: Merit percentage notification, range notification, basic merit guidelines (Merit Liaisons & all FDs) | Letter | 2010-09-15 | One-time | Same document as #5 but with a bit more data. | Merit Liaisons & all FDs | Louis Lemieux | Staff | Michelle
7 | Faculty merit guidance | Letter | 2010-09-15 | One-time | Describes merit pool, any holdback, etc. | Deans | Steven Lerman | Faculty | Liz
8 | Creation and distribution of letters to employees impacted by grade minimum change | N/A | 2010-09-20 | One-time |  |  | Louis Lemieux | Staff | Michelle
9 | FAQ's | Webpage | 2010-09-30 | One-time | Can't finish web page until we have clarification from on dates. | University Staff | Louis Lemieux, Sara Melita | Staff | Michelle
10 | Create additional webpage content | Webpage | 2010-09-30 | One-time | Can't finish web page until we have clarification from on dates. | University Staff | Louis Lemieux, Sara Melita | Staff | Michelle
11 | Final approval of merit increases | Email | 2010-12-08 | One-time | All merit increases have been approved based on final submission of data. You may notify employees starting XX and after package date. | Merit Liaisons & all FDs | Louis Lemieux, Vaness Rose, Lou Katz | Staff | Michelle
12 | Merit Packages | Letter | 2010-12-08 | One-time | Decision being made if this will be templates or actual packages. If templates, the date will have to be moved up. | Merit Liaisons & all FDs | Louis Lemieux, Sara Melita | Staff | Michelle
13 | Creation of merit worksheet guidance (first tab of merit workbooks) | XLS |  | One-time |  |  |  | Staff
14 | Reminder emails to merit liaisons to return final spreadsheets on or before 11/15 | XLS | 10/28, 11/3, 11/9, 11/15, | Every 4 days until s/s returned | Mitigation for risk of late spreadsheets | Merit Liaisons & all FDs | None | Staff | Michelle

## Travel Communications
# | Communication | Medium | Creation Date | Delivery Date | Status | Frequency | Description/Notes | Audience | Reviewer | Owner
2 | Finance Director Discussions | Meeting | 2011-12-13 | 2011-12-20 | closed | monthly | timeline strategy for travel/expense portals | Finance Directors | Donna | Rebecca
5 | 1500 x 1122 size banner image | logo | 2012-01-06 | 2012-01-06 | closed | 1 time | Josh S. send to Josh V. who will use this and resize for appropriate usage on website, lower case y pushes ibuy up, can the designer modify this? John will make a modification to the logo to fix this. | all users | Donna | Josh S.
6 | Banner for AMEX site | logo | 2012-01-06 | 2012-01-09 | closed | 1 time | linear banner for amex site (upper left corner) | all users | Donna | Josh S.
7 | Release form to AMEX for banner logo | logo | 2012-01-09 | 2012-01-14 | closed | 1time | Donna sent letter to Stephanie Baldwin in OGC |  | Donna | Donna
3 | FAQs | website | 2011-12-23 | 2012-01-23 | closed | 1 time | Use AMEX FAQs as a starting point, modify per GW specific information | All Users | Donna | Donna & Marguerite
11 | Setup Website | website | 2012-01-09 | 2012-01-23 | closed | 1 time | Design 4 logos, 4 quadrants, links to Communication content below each button | All Users | Donna | Josh Rubin/Josh Van Nuys
12 | iBuy Travel coming soon! Expense/pCard coming soon! | website | 2011-12-23 | 2012-01-23 | closed | 1time | Add these to the Travel Portal Website, must be posted when site goes live. | All Users | Donna/ Leah/Josh | Josh Rubin/Josh Van Nuys
15 | resolve issue with ibuy.gwu.edu landing page | website | 2011-12-23 | 2012-01-23 | closed | 1time | we need to make sure that the user experience on the ibu landing page is the same for those typing a URL and those finding the website via mygw. | all users | donna | donna
16 | logo design, waiting for latest revisions | website | 2011-12-23 | 2012-01-23 | closed | 1 time | design logo for iBuy Travel and Expense/Pcard | all users | Donna | Leah/Josh
1 | set up a meeting with Dave and Dave to review the web page | Meeting | 2012-01-24 | 2012-01-24 | closed | 1 time | Adam and Donna meet with Dave L. to review the web page pdf and will get back to us. | Dave L. | Donna | Donna
8 | Order 1000 luggage tags from Amex | promotional pieces | 2012-01-06 | 2012-01-31 | closed |  | will ship on 1/23/12, should take 5-7 days to receive | all users | Donna | Rebecca
4 | Executive Adoption Communications | memo/email | 2012-02-01 | 2012-02-08 | closed | 1 time | From Lou/Lerman/Dave Lawlor to all departments - talking points: easier way to book travel and rapid expense process, mention which groups are in the Pilot Group. Dave & Dave will talk with Lou, Lou will talk with Lerman. Email should come from Lou/Lerman, Donna sent it to Dorinda can the team be blind copied on this? | Dept and School Leadership | Dave L/Donna | Leah/Josh
19 | email going from Donna to the Pilot Groups ahead of profile activation on 2/8 giving them instructions and the URL. | email | 2012-01-30 | 2012-02-08 | closed | 1 time | email going from Donna to the Pilot Groups ahead of profile activation on 2/8 giving them instructions and the URL., details for 1 hour online training session | Pilot Group Users | Donna | Rebecca
18 | reminder email to Pilot Group for training session | email | 2012-02-07 | 2012-02-09 | closed
14 | get pricing on postit notes | promotional pieces | 2012-01-24 | 2012-02-16 | Hold | 1 time | Donna with send logo specs to Josh as soon as she selects the product. | All Users | Donna | Donna
20 | Training Sessions for Travel Arrangers / Pilot Group | online | 2012-01-25 | 2012-02-16 | closed | 1 time |  | Pilot Group Users | Donna | Rebecca
10 | ER- Develop content for color flyer | flyer | 2012-02-13 | 2012-02-17 | closed | 1 time | Design a flyer for email distribution, not intended to be printed. Purpose is to market iBuy Travel and contest. 1st free airfare, free meal and one night stay in DC hotel for two, free 1 week car rental, announced in the 15 day pre-launch email | all users | Donna | Josh
13 | ready to preview | flyer | 2012-02-17 | 2012-02-20 | closed | 1 time | review the 1st draft of the flyer | allusers | Donna
21 | Launch Day Announcement Pilot Group | email | 2012-02-15 | 2012-02-22 | closed | 1 time | Donna create email to Pilot send on 2/22 | Pilot Group Users | Donna | Rebecca
22 | ER - 15 days before launch - use infomail | info mail | 2012-02-23 | 2012-03-01 | closed | 1 time | ER will review the mail by 2/23/12, Lou has to approve, send flyer about contest, with link Awareness of Travel system. Focus on benefits of using the system including: user profile settings allowing frequent flyer miles to be credited, discounted travel yielding financial savings for department and ease of use and expense reimbursement system in October. Set user profile Link to web for more info. Promote the 3 prize giveaway. DO NOT include any links for access to the system. | all users | Donna | Rebecca
25 | Feedback Mechanism (setup email address, survey?) | email/survey | 2012-02-23 | 2012-03-08 | closed | continuous |  | All Users | Donna | Rebecca
23 | Training Sessions for Travel Arrangers / All Users | online | 2012-02-23 | 2012-03-20 | closed | multiple | multiple sessions | All Users | Donna | Rebecca
26 | ER - Day of Launch - use infomail | info mail | 2012-03-15 | 2012-03-22 | closed | 1 time | Need Lou's approval for this.Remind them about the contest. Do you have any upcoming work travel plans? Book with GW XXXXXX. Announcing the system is ready. Reminder to set up user profile. Link to website containing more information, FAQs | all users | Donna | Rebecca
27 | ER - Day of Launch | GW Today Article |  | 2012-03-22 | open | 1 time | Josh will check with Leah on this. Include profile activation instructions | all users | Donna | Rebecca
24 | Training Sessions for All Users | online | 2012-02-23 | 2012-03-27 | open | multiple | multiple sessions | All Users | Donna | Rebecca
9 | Order 500 AMEX drawstring bag | promotional pieces | 2012-01-06 | ?? | closed | 1 time | Rebecca order 500 from Cindy at AMEX | all users | Donna | Josh S.
31 | Contest- announce winner | email |  | 2012-05-09 | Open | 1 time | Win prizes by booking travel from March 22 through May 7, 2012: | all users | Donna | Donna
29 | ER - Post Launch | email |  | various | open | multiple | Targeted email to specialized groups | All Users | Donna | Donna
30 | ER - Peak Travel Time | email |  | various | open | multiple | Reminder email | All Users | Donna | Donna
17 | request names and email addresses for UAT group, Alumni Relations & development, biostats, Health Policy, UMC | email | 2012-01-24 |  | closed | 1 time | Trina's group will not participate in Pilot, except for those who did UAT | Pilot Group Users | donna | Rebecca
SAMPLE
This is a sample of a Communications Matrix used for a real project.

## Open Enrollment Communications
Population | Identical Text | Communication | Medium | Description | Population | Content Owner | Content Due By | BA/HR Review By | External Relations Review By | MCS Draft 1 to BA By | BA Revise By | MCS Final to BA By | BA Approval (ü) | MCS Prep Date (USPS) | InfoMail Prep Date | Distribution Date | Status
Active | A | Open Enrollment Announcement | InfoMail | Letter with Open Enrollment header and footer Letter describes what is new for 2013 Letter highlights how to enroll who to call, what to do HTML Hyperlinked to Open Enrollment Ben Admin Web Site Determine who will 'author" | All Benefit Eligible Faculty and Staff | HR/BA | 2012-08-15 | 2012-08-17 | 2012-08-21 | 2012-08-28 | 2012-08-28 | 2012-09-05 |  | N/A | 2012-09-05 | 2012-09-12
Active | A | Open Enrollment Announcement Self Mailer | Mail | Letter with Open Enrollment header and footer Letter describes what is new for 2013 Letter highlights how to enroll who to call, what to do Determine who will 'author" | All Benefit Eligible Faculty and Staff without @gwu.edu email addresses | HR/BA | 2012-08-15 | 2012-08-17 | 2012-08-21 | 2012-08-28 | 2012-08-28 | 2012-08-29 |  | 2012-08-29 | N/A | 2012-09-12
Active |  | Open Enrollment Poster Letter to recipients | Campus Mail | Letter describing purpose of the Poster | Faculty and Staff Spaces (Department Chairs, Rice Hall, Ashburn, Mount Vernon, Marvin Center Staff Offices, Town House Offices, Dean Departments) | Dan Warwick | 2012-08-15 | 2012-08-17 | N/A | N/A | 2012-08-28 | N/A |  | N/A | N/A | 2012-09-12
Active | B | Open Enrollment Posters- Benefit Fair | Campus Mail | Fair Dates Where to view the guide online* | Faculty and Staff Spaces (Department Chairs, Rice Hall, Ashburn, Mount Vernon, Marvin Center Staff Offices, Town House Offices, Dean Departments) | Dan Warwick | 2012-08-15 | 2012-08-17 | 2012-08-21 | 2012-08-28 | 2012-08-28 | 2012-08-29 |  | 2012-08-29 | N/A | 2012-09-14
Active | B | Benefits Fairs Announcement | Infomail | Fair Dates Where to view the guide online* HTML Hyperlink to Open Enrollment Ben Admin Web Site | All Benefit Eligible Faculty and Staff | Dan Warwick | 2012-08-29 | 2012-08-31 | 2012-09-04 | 2012-09-10 | 2012-09-10 | 2012-09-17 |  | N/A | 2012-09-17 | 2012-09-25
Active | B | Open Enrollment Reminder 1 | InfoMail | ONE WEEK UNTIL OPEN ENROLLMENT Fair Dates Where to view the guide online* HTML Hyperlink to Open Enrollment Ben Admin Web Site | All Benefit Eligible Faculty and Staff | Dan Warwick | 2012-08-29 | 2012-09-05 | 2012-09-10 | 2012-09-17 | 2012-09-17 | 2012-09-24 |  | N/A | 2012-09-24 | 2012-10-01
Active | B | Open Enrollment Reminder 2 | InfoMail | OPEN ENROLLMENT BEGINS TODAY Fair Dates Where to view the guide online* HTML Hyperlink to Easy Enroll Log In Page | All Benefit Eligible Faculty and Staff | Dan Warwick | 2012-09-07 | 2012-09-12 | 2012-09-17 | 2012-09-24 | 2012-09-24 | 2012-10-01 |  | N/A | 2012-10-01 | 2012-10-08
Active | B | Open Enrollment Reminder 3 | InfoMail | ONE WEEK LEFT FOR OPEN ENROLLMENT Fair Dates Where to view the guide online* Modify HTML to remove fair dates HTML Hyperlink to Easy Enroll Log In Page | All Benefit Eligible Faculty and Staff | Dan Warwick | 2012-09-19 | 2012-09-25 | 2012-10-01 | 2012-10-08 | 2012-10-08 | 2012-10-15 |  | N/A | 2012-10-15 | 2012-10-22
Active |  | Open Enrollment Final Day Reminder | InfoMail | THE FINAL DAY FOR OPEN ENROLLMENT HTML Hyperlink to Easy Enroll Log In Page | All Benefit Eligible Faculty and Staff | Dan Warwick | 2012-09-24 | 2012-10-01 | 2012-10-05 | 2012-10-12 | 2012-10-12 | 2012-10-19 |  | N/A | 2012-10-19 | 2012-10-26
Active |  | Open Enrollment Post Cards | Mail | Fair Dates Where to view the guide online* | All Benefit Eligible Faculty and Staff | Dan Warwick | 2012-08-16 | 2012-08-24 | 2012-08-29 | 2012-09-05 | 2012-09-05 | 2012-09-12 |  | 2012-09-12 | N/A | 2012-09-26
Active |  | One Page Enrollment Sheet | Printed for Fair and Web Site | Using the Easy Enroll System | Printed for General Distribution and display at Benefit Fairs | Dan Warwick | 2012-08-29 | 2012-09-04 | 2012-09-10 | 2012-09-17 | 2012-09-17 | 2012-09-24 |  | 2012-09-24 | N/A | 2012-10-08
Active | C | Full Enrollment Guide | Selective Print Web Site | Full Guide Description of Benefits, Rates, Carrier Contact Information | Web Post | Dan Warwick/ Jennifer Lopez/ Janet Monaco | 2012-08-13 | 2012-08-17 | 2012-08-24 | 2012-08-31 | 2012-08-31 | 2012-09-07 |  | 2012-09-07 | 2012-09-14 | 2012-09-21
Active | C | Separated Enrollment Resources Page | Web Site | Carrier Information Sheet | Web Post | Dan Warwick | 2012-08-13 | 2012-08-17 | N/A | 2012-08-31 | 2012-08-31 | 2012-09-07 |  | 2012-09-07 | 2012-09-14 | 2012-09-21
Active | C | Separated Medical Comparison Chart | Web Site | Comparison grid of the UHC Choice, Blue and Buff plans. | Web Post | Dan Warwick | 2012-08-13 | 2012-08-17 | N/A | 2012-08-31 | 2012-08-31 | 2012-09-07 |  | 2012-09-07 | 2012-09-14 | 2012-09-21
Active | C | Separated Rx Co-Pay Structure Page | Web Site | Prescription Coverage Explanation | Web Post | Dan Warwick | 2012-08-13 | 2012-08-17 | N/A | 2012-08-31 | 2012-08-31 | 2012-09-07 |  | 2012-09-07 | 2012-09-14 | 2012-09-21
Active | C | Separated Enrollment Rates | Web Site | 2013 Active EE-LOA Contribution Rates | Web Post | Dan Warwick | 2012-08-13 | 2012-08-17 | N/A | 2012-08-31 | 2012-08-31 | 2012-09-07 |  | 2012-09-07 | 2012-09-14 | 2012-09-21
Active | C | Separated Resident Enrollment Rates | Web Site | 2013 Resident Contribution Rates | Web Post | Dan Warwick | 2012-08-13 | 2012-08-17 | N/A | 2012-08-31 | 2012-08-31 | 2012-09-07 |  | 2012-09-07 | 2012-09-14 | 2012-09-21
Active |  | Rx Mail Order 2013 Change | InfoMail | Describe maximum monthly allowances and mail order requirement for maintenance medications. | Web Post | Dan Warwick | 2012-08-29 | 2012-09-05 | 2012-09-10 | 2012-09-17 | 2012-09-17 | 2012-09-24 |  | N/A | 2012-09-24 | 2012-10-01
Active |  | SBC (Summary of Benefits & Coverage) | Web Site / InfoMail | Standardized format and description of medical benefits and coverage. | Web Post | UHC | 2012-09-17 | 2012-09-25 | N/A | N/A | 2012-10-01 | N/A |  | N/A | 2012-10-01 | 2012-10-08
All |  | Open Enrollment Web Site | Ben Admin Web Site | Benefits Administration Page for all Open Enrollment and related Information Including Each Open Enrollment Communication Hyperlink to Easy Enroll Log In Page | Web Post | Dan Warwick/ Sara Massino | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 2012-09-05
Active |  | Open Enrollment Web Site- Temporary Landing Page | www.BeneDetails.gwu.edu/OpenEnrollment | Open Enrollment Coming Soon Landing Page prior to 2013 Application Becoming Available Open Enrollment Header and Footer Required | Web Post | Dan Warwick/ Sara Massino | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 2012-09-05
Active |  | FSA Reminder | Mercer Blast Email | Reminder that they must re-elect FSA and Reminder of grace period dates HTML Hyperlink to Easy Enroll Log In Page | All FSA Participants from previous (current) plan year | Dan Warwick | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 2012-10-19
Active |  | GWeb Banner Advertisement | Web Post | Open Enrollment Logo with a hyperlink to Easy Enroll HTML Hyperlink to Easy Enroll Log In Page | Web Post | Dan Warwick | N/A | N/A | N/A | N/A | N/A | 2012-09-21 |  | N/A | N/A | 2012-10-08
Active |  | Portal "Employee Information" Open Enrollment Link | Web Post | Link on Gweb Information Systems to EasyEnroll Log In Page | Web Post | Dan Warwick | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 2012-10-08
Active |  | GW Today Announcement | Web Post | Announcement about Open Enrollment Season Link to Open Enrollment Web Site | Web Post | Dan Warwick | N/A | N/A | Post is coordinated between ER and MCS. | N/A | N/A | 2012-09-28 |  | N/A | N/A | 2012-10-01
Active |  | Open Enrollment Map (Work/Life Fair) | Print | Map indicating provider/vendor stations | Benefit Fair Attendees | Dan Warwick | 2012-09-17 | N/A | N/A | N/A | Coordinated with BA and printed by HR. | N/A |  | N/A | N/A | 2012-10-08
Active |  | Two Gator Boards | Print | To be placed outside each ballroom entrance | Benefit Fair Attendees | Dan Warwick | 2012-08-31 | 2012-09-07 | N/A | 2012-09-12 | 2012-09-21 | 2012-09-21 |  | 2012-09-21 |  | 2012-10-08
Active |  | Open Enrollment Fair Signs | Print | Carrier Signs, Benefit Fair Signs, Large Sign regarding "If you don't enroll or make changes" and FAQ for Enrollment | Print for Fair | Dan Warwick | 2012-09-14 | 2012-09-18 | N/A | 2012-09-17 | 2012-09-19 | 2012-09-21 |  | 2012-09-21 | N/A | 2012-10-01
Active |  | University Calendars | Web Post | Calendars a. myGW Calendar: http://my.gwu.edu/mod/calendar/default.cfm?option=day b. GWired Calendar/ Do This: http://gwired.gwu.edu/submit.php c. Hatchet Calendar (print): calendar@gwhatchet.com d. Hatchet Calendar (web): http://gwhatchet.com/calendar/ 2- Portal Feature - available only when signed-on (non-public view) | All Benefit Eligible Faculty and Staff | Dan Warwick | N/A | N/A | N/A | N/A | N/A | 2012-09-21 |  | N/A | N/A | 2012-09-28
Active |  | Update Backup Enrollment Forms | Paper | Update Paper Enrollment Form for Participants that are unable to use Enrollment System | All Benefit Eligible Faculty and Staff | Dan Warwick/ Sara Massino | 2012-09-17 | 2012-09-21 | N/A | N/A | 2012-10-01 | N/A |  | N/A | N/A | 2012-10-08
Retiree |  | Open Enrollment Announcement Self Mailer | Mail | Letter with Open Enrollment header and footer Letter describes what is new for 2013 Letter highlights how to enroll who to call, what to do Full guide description of benefits, rates and vendor contact information. enrollment form | Retirees, LOA, LTD COBRA participants | HR/BA | 2012-08-15 | 2012-08-17 | 2012-08-21 | 2012-08-28 | 2012-08-28 | 2012-09-04 |  | 2012-09-11 | N/A | 2012-09-25
Retiree |  | Open Enrollment Postcard - ONE VERSION FOR ALL R/L/C population | Mail | Open Enrollment Dates / enrollment kit | Retirees, LOA, LTD COBRA participants | Dan Warwick/Cara Shumate | 2012-08-15 | 2012-08-17 | 2012-08-24 | 2012-08-31 | 2012-08-31 | 2012-09-06 |  | 2012-09-13 | N/A | 2012-09-27
Retiree |  | Cover Letter, Enrollment Guide, Rate Information and Enrollment Form | Mail | Cover letter and application/Enrollment Guide & Rates | Retirees, LOA, LTD COBRA participants | Dan Warwick/Cara Shumate/PayFlex | 2012-08-15 | 2012-08-17 | 2012-08-21 | 2012-08-28 | 2012-08-28 | 2012-09-04 |  | 2012-09-10 | N/A | 2012-09-24
LTD |  | Open Enrollment Announcement Self Mailer | Mail | Letter with Open Enrollment header and footer Letter describes what is new for 2013 Letter highlights how to enroll who to call, what to do Letter body authored by HR. Full guide description of benefits, rates and vendor contact information. enrollment form | Retirees, LOA, LTD COBRA participants | HR/BA | 2012-08-15 | 2012-08-17 | 2012-08-21 | 2012-08-28 | 2012-08-28 | 2012-09-04 |  | 2012-09-11 | N/A | 2012-09-25
LTD |  | Open Enrollment Postcard - ONE VERSION FOR ALL R/L/C population | Mail | Open Enrollment Dates / enrollment kit | Retirees, LOA, LTD COBRA participants | Dan W./Kim V. | 2012-08-15 | 2012-08-17 | 2012-08-24 | 2012-08-31 | 2012-08-31 | 2012-09-06 |  | 2012-09-13 | N/A | 2012-09-27
LTD |  | Cover Letter, Enrollment Guide, Rate Information and Enrollment Form | Mail | Cover letter and application/Enrollment Guide & Rates | Retirees, LOA, LTD COBRA participants | Dan Warwick/Kim V./PayFlex | 2012-08-15 | 2012-08-17 | 2012-08-21 | 2012-08-28 | 2012-08-28 | 2012-09-04 |  | 2012-09-10 | N/A | 2012-09-24
COBRA |  | Open Enrollment Announcement Self Mailer | Mail | Letter with Open Enrollment header and footer Letter describes what is new for 2013 Letter highlights how to enroll who to call, what to do Letter body authored by HR. Full guide description of benefits, rates and vendor contact information. enrollment form | Retirees, LOA, LTD COBRA participants | HR/BA | 2012-08-15 | 2012-08-17 | 2012-08-21 | 2012-08-28 | 2012-08-28 | 2012-09-04 |  | 2012-09-11 | N/A | 2012-09-25
COBRA |  | Open Enrollment Postcard - ONE VERSION FOR ALL R/L/C population | Mail | Open Enrollment Dates / enrollment kit | Retirees, LOA, LTD COBRA participants | Dan Warwick | 2012-08-15 | 2012-08-17 | 2012-08-24 | 2012-08-31 | 2012-08-31 | 2012-09-06 |  | 2012-09-13 | N/A | 2012-09-27
COBRA |  | Cover Letter, Enrollment Guide, Rate Information and Enrollment Form | Mail | Cover letter and application/Enrollment Guide & Rates | Retirees, LOA, LTD COBRA participants | Dan Warwick/Kim Vanlewen/PayFlex | 2012-08-15 | 2012-08-17 | 2012-08-21 | 2012-08-28 | 2012-08-28 | 2012-09-04 |  | 2012-09-10 | N/A | 2012-09-24
SAMPLE
This is a sample of a Communications Matrix used for a real project.

## eExpense Communications
# | Type | Communication | Medium | Creation Date | Delivery Date | Status | Frequency | Description/Notes | Audience | Reviewer | Owner
2 | Branding | Login Experience for Concur Expense Solution | logo/website | 2012-05-01 | 2012-07-30 | Closed |  | 7/30 - ER web team determined best to go to Concur Expense or Concur Travel. Adam to work with UWS 7/19 - ER looking into user feedback to determine login experience. Update expected 7/30 6/20 - mtg scheduled to review with Deb, Donna and Dave on 7/16; to discuss with project team at 7/19 mtg 6/4 - Leah to review with her team, make recommendation to Dave 5/22 - Adam discussed with Deb and Donna who agreed to single login. Adam to discuss with Dave. 5/1 - Determine how to utilize "My Concur" (combo of e-expense and travel portal), where to direct users. Also need to combine logos for e-expense and pcard. Then need to work with ER, project team to develop marketing plan. | All Users | Dave | Adam
3 | Branding | Name and logo for system | logo/website | 2012-06-04 | 2012-07-19 | Closed |  | 7/19 - agreed that ibuy+ will be used with Expense showing as available option 6/20 - mtg scheduled to review with Deb, Donna and Dave on 7/16; to discuss with project team at 7/19 mtg 5/1 - Work with External Relations to develop name and logo for system | All Users | Deb, Donna/Dave | ER
54 | Branding | Appropriate logos for Travel Booking, Expense Reporting, Goods & Services, iBuy+ | logo/website | 2012-08-01 | 2012-10-29 | Closed |  | multiple logos for system, websites, e-mail headers | All Users | Megan | ER
1 | Communication | Communications Plan (Draft) | Plan | 2012-05-01 | 2012-06-21 | Closed |  |  | Project Owners | Adam, External Relations | Megan
8 | Communication | Web Page (Draft) | website | 2012-07-02 | 2012-08-24 | Closed | - | Website map has been developed; awaiting UWS to determine if resource for web development is available | All Users | Donna, Deb | Lennox, Josh R, George
10 | Communication | 1st draft e-mail(s) (for review with Executive Sponsors) | e-mail | 2012-06-17 | 2012-08-16 | Closed | - | 7/30 - given to ER for review, awaiting Leah's return on 8/13 | All Users | Dave | Megan
11 | Communication | Communications Plan (for review by Executive Sponsors) | Plan | 2012-06-04 | 2012-08-16 | Closed | 1 time | 8/8 - review with Deb & Donna 7/30 - given to ER for review, awaiting Leah's return on 8/13 | Executive Sponsors | Dave | Megan
12 | Communication | E-mail to UAT Participants (to include training, session info) | e-mail | 2012-08-02 | 8/8, 8/16 | Closed | 2 times | 1st e-mail ready to send. Requesting RSVP on which session (& training) they will attend | UAT | Jeff | Megan
14 | Communication | Targeted Discussion with Finance Directors | Meeting | 2012-05-01 | 9/18, 11/20 | Closed | 2 times | During Sept mtg, we will address training, expected changes, etc (confirmed with Ed on 8/13 that we are on the schedule); Nov mtg will focus on reports | Finance Directors |  | Megan
16 | Communication | Deployment e-mail to managers/executives to engage help in communicating pending change | e-mail | 2012-07-26 | 2012-09-05 | Closed | 1 time | e-mail is with ER; ER recommends all e-mails come from Lou; need to contact Steve Lerman's and Lou's offices to know right lists to send this to | GW Managers, Supervisors | Dave | Megan
17 | Communication | New Expense Reporting web pages (Information & Training) | website | 2012-08-01 | 2012-09-11 | Closed |  | Needs to launch before first e-mail announcement; 2 new web pages to include Expense Reporting (1) Info & (2) Training | All Users | Deb, Donna | Lennox, Josh R, George
18 | Communication | Update to FOPS meeting participants | Meeting | 2012-05-24 | 2012-09-21 | Closed | 1 time | 8/31 FOPS mtg? | Senior level leaders in EVP&T and OVPR | Dan | Megan
19 | Communication | Announcement e-mail to all GW staff and faculty | e-mail | 2012-05-01 | 9/12, 10/16 | Closed | 2 times | ER has recommended only 2 e-mails - 9/12 and 10/16 | GW Staff, Faculty, Researchers | Dave | Megan
20 | Communication | Targeted e-mail to P-Card users | e-mail | 2012-05-01 | bi-weekly starting 9/18 | Closed | 5 times | notifying users of system change, timeline (need to complete Oct reports by 10/26) | PCard holders, report approvers | Donna | Megan
21 | Communication | Targeted OVPR/Researchers Discussion | Meetings | 2012-05-01 | 9/6, 10/3, 10/18 | Closed | 1 time | announcements at monthly mtg of Associate Deans for Research + monthly CRAG mtgs (possibly at wkly OVPR staff mtg, too) | Research Staff | Dan | Megan
22 | Communication | Targeted Faculty Discussion | Meetings | 2012-05-01 | Sept-Oct | Closed | 1 time | e-mailed all Deans' special assistants, participated in dept meetings in SEAS, CCAS and SMHS could possibly use FDs, or see if scheduled Deans/departmental meetings that we could visit to make an announcement | Faculty | Dan | Megan
23 | Communication | Targeted Administrative Assistants Discussion | e-mail | 2012-05-01 | Sept-Oct | Closed | 1 time | 10/29 - administrative assistants e-mailed with helpful tips, offers of assistance 8/27 - administrative assistants e-mailed to help with communication efforts; Dan spoke at dept mtgs where we were able to get on schedule check with Dorinda to see if there is a way to get targeted message to administrative support staff in executive's offices | Administrative Staff | Dan | Megan
24 | Communication | Announcement e-mail upon deployment | e-mail | 2012-07-30 | 2012-10-29 | Closed | 1 time | Sent on 10/31 | GW Staff, Faculty, Researchers | Dave | Megan
27 | Communication | Banner Announcement in Pathway.net system | System Announcement | 2012-09-01 | 2012-09-14 | Closed | 1 time | George noted he coud add banner information in Pathway.net that will show up for all users in system (he has tested and is working with Roger to make it presentable) | P-Card holders | Donna | George
28 | Communication | Pop up message in EAS for users submitting Online Travel & Expense Reimbursement | System Announcement | 2012-09-01 | 2012-09-14 | Closed | 1 time | Anna to submit ticket for this, once language is approved | GW Employees | Deb | Lennox
29 | Communication | E-mail to ibuy users to alert change in name, web links | e-mail | 2012-07-16 | 2012-09-05 | Closed | 1 time | 7/30 - waiting for ER to determine date of ibuy+ roll-out. E-mail would go out one week prior to roll-out | ibuy users | Donna | Megan/Josh
30 | Communication | Updated ibuy pages | website | 2012-08-02 | 2012-09-12 | Closed |  | changing references from iBuy to 'Goods & Services' awaiting feedback from ER on launch date of ibuy+. If it is included in all language, launch may need to be 9/5. Recommend incorporating ibuy changes before 10/29 go-live date | All Users | Donna | Josh
31 | Communication | Update ibuy Central logos to ibuy+ | website | 2012-07-30 | 2012-09-12 | Closed |  | ER to create ibuy+ logo images to use on web page. Will need to update all buttons, banners, etc. referencing ibuy Central | All Users | Donna | Josh
32 | Communication | Update links to EAS T&E and to P-Card to ibuy+ | website | 2012-09-01 | 2012-10-29 | Closed |  | UWS will need this information, including when to re-route and where | All Users | Dan, George | Anna, Josh
33 | Communication | Add announcement, links to P-Card and AP pages | website | 2012-09-01 | 2012-09-12 | Closed |  | Announcements added when website went live | All Users | Dan, George | Megan
36 | Communication | Targeted communication with Deans | Meeting | 2012-08-01 | 2012-09-15 | Closed | 1 time | contacted Provost office to get on agenda at Council of Deans meeting; created flier for 9/6 meeting, Deans responded with questions that were answered for 9/13 mtg | School Deans | Deb | Megan
38 | Communication | Email to those who run BPRs to let them know of expected changes to report | e-mail | 2012-07-26 | 2012-10-26 | Closed | 1 time | e-mails sent through EAS on 10/26 | Finance Directors, other financial admins | Sharon | Kevin
39 | Communication | Reminders to PCard holders to allocate pre-10/20 charges by 10/26; Reports to FDs on who has unsubmitted PCard reports | e-mail | 2012-10-01 | 2012-10-29 | Closed | 3 times | George to send e-mails to PCard holders with unsbumitted charges, list to FDs throughout week to ensure employees allocate on time | PCard holders | George | George
40 | Communication | E-mail to Travel listserv regarding addition of expense | e-mail | 2012-10-01 | 2012-10-29 | Closed | 1 time | Marguerite sent msg on 10/18 to Travel listserv making users aware of change to system | Travel users | Marguerite | Megan
42 | Communication | Communication to MFA regarding system | e-mail | 2012-10-01 | 2012-10-31 | Closed | 1 time | Dan sent message to PCard holders from MFA who will be added to system | MFA | Dan | Dan
43 | Communication | Targeted discussion with Finance Directors on issues users are experiencing in first month of system usage | meeting | 2012-11-01 | 2012-11-21 | Closed | 1 time | Dan e-mailed FDs to gather input on issues users are having; addressed in November FD mtg | Finance Directors | Dan | Dan
47 | Communication | Web Mods and Links Matrix | website | 2012-08-01 | 2012-09-05 | Closed | 1 time | Updates to links once new Expense system, iBuy+ site goes live | All Users | UWS | Josh
48 | Communication | Login Page for Expense System | website | 2012-10-01 | 2012-10-29 | Closed | 1 time | Separate login page (from Travel Booking) with Expense Reporting logo | All Users | Josh | Tochi
49 | Communication | Updates to Expense System pages on go-live date | website | 2012-09-05 | 2012-10-29 | Closed | 1 time | Updates to PCard, Reimbursement, FAQs pages; add Contact Us page with Concur helpdesk # | All Users | Adam | Megan
50 | Communication | Redirects for 10/29 | website | 2012-10-01 | 2012-10-29 | Closed | 1 time | Updates to Procurement/PCard links once system goes live | All Users | UWS | Josh
51 | Communication | Link on AP site to Expense Reporting system; Updates to appropriate AP forms | website | 2012-10-30 | 2012-11-01 | Closed | 1 time | Add link to Expense Reporting system to sidebar of AP site | All Users | Deb | Shelley
4 | Training | Training Plan (Draft) | Plan | 2012-06-18 | 2012-08-06 | Closed | - | final draft to be ready by 8/16 for mtg with executive sponsors | Project Team | Deb, Donna | Lennox
5 | Training | Quick Reference Guides to Expense System (for UAT) | Manual | 2012-06-20 | 2012-08-13 | Closed | 1 time | Downloadable easy to read, easy to understand instruction manual (how to clear expenses, how to scan receipts, how to allocate expenses, how to approve, etc.) 5/1 - Start with Concur template (in eroom/Communications folder) | UAT | Lennox | Jen Whaley
6 | Training | FAQs (for UAT) | website | 2012-06-04 | 2012-08-13 | Closed | 1 time | Use Concur FAQs as a starting point, review other university's FAQs, modify with GW specific information | UAT | Lennox | Megan
7 | Training | Captivate Sessions | website | 2012-09-01 | 2012-12-31 | Open | 1 time | Sept '12 - decided to focus on Captivate sessions that are different than Concur videos and will be most useful; goal to have two completed by Nov 2012 these will be done after UAT, with FSS possibly owning their creation. They will be based on the Quick Reference Guides that are already created. Shelley in AP has been given a license to to handle ongoing maintenance of trainings | All Users | Deb, Donna | Lennox
9 | Training | Training Plan (for review by Executive Sponsors) | Plan | 2012-06-18 | 2012-08-16 | Closed | - | to include in Deployment Plan. Includes objectives, participants, materials, methods, resources, schedule, and evaluation | Executive Sponsors | Dave | Lennox
13 | Training | Training Session for UAT participants | Training Session | 2012-08-16 | 8/20, 8/23, 8/28 | Closed | 3 sessions | Lennox will facilitate these. In addition, UAT participants will be provided with paper copies of Quick Reference Guides for basic functions | UAT | Jeff | Lennox
15 | Training | Updated Training Materials, based on feedback from UAT | website | 2012-09-10 | 2012-09-12 | Closed |  | Updated Quick Reference Guides & FAQs + Updated Content for webinars | All Users | Deb, Donna | Lennox
25 | Training | Live Training Sessions for All Users (on campus) | Training Session | 2012-09-17 | 9/24-10/16 | Closed | 16 times | Beginning 9/17, 2 trainings per week; Beginning 10/1, 3 trainings per week; Locations to vary and include FB, Ashburn, Biostats Center | GW Staff, Faculty, Researchers | Deb, Donna | Lennox
26 | Training | Live Training Sessions for All Users (virtual, using Elluminate) | Training Session | 2012-09-17 | 9/24-11/15 | Closed | 1/wk | Determined that following launch, virtual trainings will be utilized rather than live trainings. Frequency may increase (as demand requires) after 10/29 go-live date | All Users | Deb, Donna | Lennox
34 | Training | Training Sheet specific to Grants | website | 2012-08-01 | 2012-09-17 | Closed | 1 time | Put info into FAQs Aileen to put together training to include any special instructions for those with grant-related expenses (users & approvers) | Research Staff | Deb | Aileen
35 | Training | Training Sheet specific to Business Intelligence Managers | website | 2012-08-01 | 2012-09-30 | Open | 1 time | Jaime to put together specific training instructions for those with BI status, on running reports, features of system, etc. | Finance Directors | Deb | Jaime
37 | Training | Targeted training with EVP&T special assistants | Training Session | 2012-10-01 | 2012-10-20 | Closed | 1 time | Training with Admin Assistants at Rice 7 | Administrative Staff | Adam | Megan
41 | Training | E-mail to training participants with most common issues seen in first week of system usage | e-mail | 2012-11-01 | 2012-11-10 | Closed | 1 time | Shelley sent message regarding delegate function on | System users | Dan | Shelley
44 | Training | Contact HR regarding New Employee Orientation, ensuring employees aware of system, how to be trained | Announcement | 2012-08-01 | 2012-11-01 | Open | 1 time | Megan contacted HR to ask about presenting information (possibly in flier format) about Expense training for new employees; AP to handle going forward | New Employees | Lennox | Megan
45 | Training | Intro slides for training session | Training Session | 2012-08-01 | 2012-09-20 | Closed | 1 time | Intro slides to use in all trainings, explaining what users can expect; what's changing and what's not changing; how to access the system; etc. | All Users | Lennox | Adam
46 | Training | One pager to hand out at training sessions | Training Session | 2012-09-01 | 2012-09-20 | Closed | 1 time | One page handout to distribute during trainings with information on what to do the first time you log into the system | All Users | Lennox | Megan
52 | Training | Updated FAQs | website | 2012-09-01 | 2012-10-29 | Closed |  | Update FAQs after UAT, training sessions | All Users | Adam | Megan
53 | Training | Recorded Training Session to post online | Training Session | 2012-10-01 | 2012-11-01 | Open | 1 time | Recorded Elluminate Session | All Users | Dan | Lennox
55 | Training | Ongoing Training Plan | Plan | 2012-08-01 | 2012-11-15 | Closed | 1 time | Plan for training users (PCard holders, new employees) past deployment | All Users | Dan | Lennox
56 | Training | Updated Training Materials in Concur System | website | 2012-10-01 | 2012-10-29 | Closed | 1 time | links to updated GW training materials from system | All Users |  | Megan
57 | Training | Survey on Training Sessions | website | 2012-09-01 | 2012-10-15 | Closed |  | Surveys on training sessions | All Users | Lennox | Megan
58 | Training | Targeted Administrative Assistants Help | phone | 2012-11-15 | 2012-11-30 | Closed |  | Calling all administrative assistants to inquire about use of the system, answer questions | Administrative Staff |  | Megan
SAMPLE
This is a sample of a Communications Matrix used for a real project.