## Risk register
Jayamahal project: Risk Register
| Group 5 | Ranjit Phaltane, Souren Laha, Siddhant, Thiyagarajan, Roshan, Ramcharit |  |  |  | 2020-04-15 | Rev: I |  |  | Risk assessment - Refer matrix
# | WBS | RBS | Risk category | Risk detail | Risk raised date | Risk owner | Risk Duaration | Schedule impact | Cost impact | Likelyhood | Impact | R (E) | Risk resonse type | Response type | Response detail | Reserve action
1 | Fish introduction | Technical | Environment management | Aquatic species will die if water O2 level is not sufficient / impure water mixes | 2020-04-12 | SME- Water engr | 1 month | 1 month | ₹ 50 crore | 50% | 50 | 25 | Threat | Mitigate | Create aritifical poind nearby & Move the species to artifical pond before chemical process begins | Additional iteration of clearning & fish introduction
2 |  |  |  | Aquatic species selected - don’t coexist after lake restoration | 2020-04-12 | Environmentalist | 1 month | 2 wk | ₹ 30 crore | 30% | 10 | 3 | Opportunity | Exploit | Hire technical experts to select fish types & check possibility of fishing in certain portions of lake - give proposal to RAJ Govt & obtain approval | NIL
3 | Plantation |  |  | Planted samplings - don’t grow as expected | 2020-04-12 | Gardener | 1 month | 1 month | ₹ 20 crore | 30% | 100 | 30 | Threat | Mitigate | Plan 20% additional samplings than necessary | Change of soil
4 | Project approval | Management | Legal | Forest dept doesn’t give permit on time, considering migration of birds (before project completes) | 2019-07-30 | Admin - legal | 14 months | 1 month | ₹ 70 crore | 50% | 100 | 50 | Opportunity | Share | Provide proposal of bird sanctuary with new bird species which would migrate after nesting island formation | NIL
5 |  |  |  | Fire safety permit delay considering work on tourist spot | 2019-07-30 | Admin - legal | 8 months | 2 months | ₹ 100 crores | 100% | 100 | 100 | Threat | Accept | Approach 1M before scheduled requirement & prrovide security details to restrict tourist flow while project work is in progress | Additional fire safety measures provisoning
6 |  |  |  | Ecological permit delay considering local sewage management (which was coming to lake earlier) disposal issues | 2019-07-30 | Admin - legal | 6 months | 1 month | ₹ 50 crore | 50% | 50 | 25 | Threat | Avoid | Provide new model for local sewage management to ecology department with all benefits | NIL
7 | ALL | Commerical | Contract risk | cost overuns in labour contracts due to delay in project activities | 2019-07-30 | Finance -contract | 15 months | - | ₹ 100 Crores | 50% | 100 | 50 | Threat | Accept | Establish review mechanism for schedule & cost performance; Conduct necessary changes to contracts at specific review points | Delay certain contracts
8 |  |  |  | Inefficient contracting - CPI (cost performance index) would be lower than 1 | 2019-12-10 | Engineering | 10 months | - | ₹ 60 crores | 30% | 50 | 15 | Opportunity | Reaseach | (1) Change to variable type contract wherever possible | Review financial contracts every month with respect to schedule performance
9 | Channel |  |  | Change in scope due to evironmental dept issue- Length of drain channel | 2020-01-10 | Engineering | 1 month | 2 wk | ₹ 10 crore | 30% | 10 | 3 | Threat | Accept | Considering low schedule & cost impact, look at accepting risk without affecting overall schedule & cost | NIL
10 | Public awareness | Management | Public related | Tourist interference | 2019-07-30 | Admin-security | 12 months | 1 month | ₹ 70 crore | 100% | 50 | 50 | Threat | Transfer | Involve client (RAJ Govt) for involving local police for enforcing law & order | Hire private security team with necessary contract
11 |  |  |  | Environmentalists protests due to drain channel | 2019-07-30 | Admin-ecology | 6 months | 1 month | ₹ 100 crores | 100% | 100 | 100 | Opportunity | Enhance | (1) Meet key ENV. members from project initiation & convince them to be enablers / stakeholders (2) Form association of environmentalists & look at possibiliities of resolving their concern through the current project objectives | Publish necessary project details & benefits to environmentalists
12 |  |  |  | Damage to contruction site / equipmenet by local business | 2019-12-01 | Admin-security | 7 months | 1 month | ₹ 70 crore | 100% | 50 | 50 | Opportunity | Share | Give proposal for additional project to RAJ Govt for creating corridor around Jayamahal palace & lake for local businesses which will increase jobs without affecting project success criteria | Send official notice to local businessmen before start of project activities
13 | ALL | Management | Labour | labour at given rate is not available | 2019-09-20 | Admin-labour | 12 months | 2 months | ₹ 110 crores | 50% | 100 | 50 | Threat | Mitigate | Propose use of labour from different places to Client & get it approved | Monitor labour rates available across country
14 |  |  |  | Labout unrest | 2019-09-20 | Admin -labour | 12 months | 2 wk | ₹ 20 crore | 30% | 10 | 3 | Threat | Mitigate | (1) Build cost & time contingency (2) Create detailed terms with contractors | Additional available labourers / contractors from different part of country
15 | Plantation |  |  | Diwali holidays causing migration of labours for a month during project completion state | 2020-07-01 | Admin-labour | 2 months | 1 month | ₹ 70 crore | 100% | 50 | 50 | Threat | Mitigate | (1) Come out with bare minimum number of labourers required during Diwali period for project schedule (2) Discuss with contractor with motivations for keeping the necessary peronnel at project site during Diwali holidays | Additional contractor for doing work during holidays
16 | - | External | Macro economy | Economic slowdown resulting in delayed release of funds | 2019-07-30 | Project management office | 15 months | 3 months | > ₹ 100 crores | 30% | 100 | 30 | Threat | Avoid | Create terms during project approval stage & highlight schedule performance depending timely availability of funds | Timely updates to Raj Govt regarding project progress & assumptions
17 | - |  | Political | Change at State Govt, may reduce project priority & release of funds | 2019-07-30 | Project management office | 15 months | > 3 months | > ₹ 100 crores | 30% | 100 | 30 | Threat | Avoid | Create terms during project approval stage & fine print schedule & cost changes on the basis of fund & neecessary resource availability & timely approvals
Note on H7: Ranjit Phaltane: Aug 19 to Proj closure

## Risk probability matrix
Risk Probability matrix
Ref: Risk analysis & Management - a vital key to effective project management; Lavanya N et al, 2008, PMI
| Probability of risk occurance |  |  |  |  | Model derived |  | Probability of risk occurance
| Probability | approx ocurrance | Indication |  |  | Probability | Column1 | Approx occurance | Indication
| High | 80% to 100% | 100% |  |  | High |  | 60 to 100 % | 100
| Medium high | 60% to 80% | 80% |  |  | Medium |  | 30 to 60% | 50
| Medium low | 30% to 60% | 60% |  |  | Low |  | 0 to 20% | 30
| Low | 0 to 30% | 30%
Risk impact
| Impact | Impact type | Rating | Indication
| High | Catastrophic | A | 100
| Medium | Critical | B | 50
| Low | Marginal | C | 10
| Project objective | C rating | B rating | A rating
| Cost | Increase > 0% | increase 5 - 10% | Increase > 10%
| Schedule | delay > 0 days | delay > 1 wk | delay > 2 wk
| Scope | barely noticebly | Minor affected | Major; not acceptable to client
| Quality | barely noticebly | doesn’t affect vital function | Requires client approval
Risk probability matrix to be used in risk register
|  | Probability | [5 empty] | Probability
| Impact | High | Medium high | Medium low | Low | Impact |  | High | Medium | Low
|  | 100% | 80% | 60% | 30% |  |  | 100% | 50% | 30%
100 | High | 100 | 80 | 60 | 30 | High | 100 | 100 | 50 | 30
50 | Medium | 50 | 40 | 30 | 15 | Medium | 50 | 50 | 25 | 15
10 | Low | 10 | 8 | 6 | 3 | Low | 10 | 10 | 5 | 3

## Response strategy
STRATEGY | TYPE OF RISK | EXAMPLES
Avoid | Threat | 1. Change project plan and/or scope
2. Improve project communications
3. Decide not to perform project
Transfer | Threat | 1. Insurance
2. Fixed-price contract
3. Hire expert
Mitigate | Threat | 1. Lower probability and/or impact of threat
2. Build in redundancy
3. Use more reliable methods
Accept | Threat and opportunity | 1. Deal with it if and when it happens
2. Establish triggers and update frequently
3. Establish time and/or cost contingencies
Research | Threat and opportunity | 1. Get more and/or better information
2. Verify assumptions
3. Use prototype
Exploit | Opportunity | 1. Assign talented resources to project
2. Give more emphasis to project
Share | Opportunity | 1. Allocate partial ownership to third party
2. Form joint venture
Enhance | Opportunity | 1. Increase probability and/or positive impact
2. Identify and maximize key drivers
3. Add more resources

## Risk planning
Group 5: Jayamahal project risks
Ranjit Phaltane, Souren
Risk planning
Objective | To complete project to satisfaction of Rajasthan Govt
To win next project
Stakeholders
Raj Govt
Public / tourist
Businessman on tourist track /area
Contractors
Suppliers
Project team
Environmental species eg fishes, trees etc ?????
Environmentalist
Veraious legal departments eg. Environment, urban planning, fire safety, forest det etc
Labourers
Risk categories
Financial mismanagement
Time overrun
Not able to able meet BOD req
Environmental species, plantation management
Legal compliances
Contract risk - fixxed or variable
Technology - imported CV / water cleaning
Labour related
Public related - tourists, local businessmen, environmentlists
Safety
Risks
Environment management
Species will die if water O2 level is not sufficient / impure water mixes
Planted samplings - don’t grow as expected
Species selected - don’t coexist
Legal
Forest dept doesn’t give permit considering migration of birds on time
Fire safety permit delay considering likely tourist spot
Ecological permit considering local sewage management (which was coming to lake earlier)
Contract risk
cost overuns in labour contracts due to delay in project activities
Pumping capacity inadequate for fountains
Length of drain channel - change in scope due to evironmental dept issue
Public related
Tourist interference
Environmentalists protests due to drain channel
Damage to contruction site / equipmenet by local business
Labour
labout at given rate is not available
Labout unrest
Diwali holidays causing migration of labours for a month during project completion state