## Group Deatils
Risk Register for Jal Mahal Project
BY
Group - 2
Srl No | ID | Name
1 | SPJ1108 | Mr. Zulukumzuk Pongen
2 | SPJ1109 | Mr. Venzil Fernandes
3 | SPJ1110 | Mr. Sridhar Subramanian Iyer
4 | SPJ1111 | Ms. Bipasha Chakraborty
5 | SPJ1112 | Mr. Debajyoti Basu
6 | SPJ1113 | Mr. Manoj Singh Chauhan

## Brief Note
A | 5 broad risks have been considered in Jal Mahal Project
1. - Environmental
2. Resource
3. Statutory
4. Quality
5. Financial
B | Under all these categories, 3 risks have been taken into account
C | The column K, viz. Risk Exposure, is a formula driven field based on Probability Impact Matrix which is stated just below the risk register. Different color codes has been put based on Risk Exposure which is also automated.
D | For ready reference, the probability Impact Matrix is also stated in the next Sheet viz. Probability_Impact_Matrx.

## Risk Register
Serial No | Risk Category | Risk Description | Schedule Impact | Cost Impact | Cause | Effect | Owner | Probability of Risk Occurance | Impact | Risk Exposure | Risk Response | Probability | Impact | Risk Exposure
1 | Environmental | Unavailability of area for muck collection | Probable delay in project | Additional cost of transportaion | Lack of adequate area for collection and disposal of muck. | Environment pollution | Project Manager | Rare | Moderate | Low | Escalation to project sponsor | Rare | Negligible | Very High
|  | Inappropriate proportion of chemical for lake cleaning | Probable delay in project | Additional cost for proper cleaning of lake | Inadequate knowledge of chemicals | Health hazard leading to death of the Fish species bringing in legal complications. | Procurement Head + Subject Matter Expert (SME) | Moderate | Severe | High | Transfer to a consulting agency | Unlikely | Minor | High
|  | Inconducive environment for plantation | Delay in project | Additional cost to meet project success criteria | Inappropriate environment | Effect on enrironment | Project manager + Environmentalist | Moderate | Moderate | Medium | Escalation to higher management | Moderate | Moderate | Medium
[12 empty] | Likely | Significant | Low
2 | Resource | Unavailability of skilled manpower | Delay in project | Additional cost for hiring manpower leading ro budget overshoot | Attrition of skilled resources. | Delay in project causing revenue loss | Project Manager | Moderate | Moderate | Medium | Mitigate with intervention of Head -HR | Very Likely | Severe | Very Low
|  | Delay in manufacturing and supply of required fountain. | Delay in project | Additional cost for hiring proper equipment leading to budget overshoot. | Delay from contractor | Delay in project causing revenue loss | Project Manager + Procurement Manager | Moderate | Significant | Medium | Avoid by Adding incentives in the contract
|  | Delay of supply of materials | Delay in project | Attracting penalty for non completion of project on time | Improper planning | Delay in project timeline | Project Manager + Procurement Head | Likely | Significant | High | Avoid by Adding incentives in the contract
3 | Statutory | Alteration of Tax structure | Delay in project | Impact on Project cost due to tax structure change | Policy change by Government on tax structure | Overshooting of budget | Procurement Head + Project Manager + CFO | Unlikely | Significant | Medium | Accept by using contigency budget
|  | Change in labor laws | No impact envisaged | Cost impact for the project | Change in statutory rules by Government | Internal Policy review | Project Manager + CFO + IR Head | Rare | Moderate | Low | Accept by using contigency budget
|  | Interference of worker union + local bodies | Probable delay in project | Arrange Resource at higher cost | Lack of proper liasoning with the local authority | Impact on schedule and Cost | Project Manager + IR Head | Moderate | Moderate | Medium | Transfer by appointing an man power supply agency
4 | Quality | Usage of un specified materials | Probable delay in project | Additional cost of rework | No standard supply of Materials by Vendor | Loss of Reputation impacting future business oppurtunity | Procurement Head + Project Manager | Moderate | Severe | High | Avoid by inspetion and scope validation
|  | Fluctuation in Oxygen levels in water harming the species | Probable delay in project | Additional cost of rework | Lack of adequate technical knowledge | Severe impact on environment and fish species | Project Manager + Environmentalist | Moderate | Severe | High | Mitigate by Technical expertise
|  | Degradation in water quality | Probable delay in project | Additional cost of rework | Lack of adequate technical expertise | Severe impact on environment and fish species | Project Manager + Environmentalist (SME) | Unlikely | Significant | Medium | Mitigate by Technical expertise
5 | Financial | Error in estimation | Probable delay in project | Cost overrun | Lack of adequate expertise | Impact on Project cost and schdule | Project Manager + Estimation Head + CFO | Unlikely | Significant | Medium | Escalation to Management
|  | Price hike of materials | Probable delay in project | Additional cost | Market driven | Impact on Project cost and schdule | Project Manager + Procurement Head + Estimation Head+ CFO | Likely | Significant | High | Escalation to Project Manager + procurement Head + Estimation Head + CFO in order to conclude
|  | Higher cost of imported CV technology | Probable delay in project | Additional cost | Incorrect estimation | Impact on Project cost and schdule | Project Manager + Estimation Head + CFO | Moderate | Significant | Medium | Avoid by Fixed price with fixed incentive contract .
Probability
|  | Rare | Unlikely | Moderate | Likely | Very Likely |  | Risk Exposure
Impact | Negligible | Very Low | Very Low | Low | Low | Medium |  | Very High
| Minor | Low | Low | Medium | Medium | Medium |  | High
| Moderate | Low | Medium | Medium | Medium | High |  | Medium
| Significant | Low | Medium | Medium | High | Very High |  | Low
| Severe | Medium | Medium | High | Very High | Very High |  | Very Low

## Probability_Impact_Matrix
Probability
|  | Rare | Unlikely | Moderate | Likely | Very Likely | Risk Exposure
Impact | Negligible | Very Low | Very Low | Low | Low | Medium | Very High
| Minor | Low | Low | Medium | Medium | Medium | High
| Moderate | Low | Medium | Medium | Medium | High | Medium
| Significant | Low | Medium | Medium | High | Very High | Low
| Severe | Medium | Medium | High | Very High | Very High | Very Low